## Project Overview
DATA CLEANING FOR EXCEL DASHBOARD ¦ Project Management Complete Reference
PROJECT INFORMATION
Project Name | Data Cleaning for Excel Dashboard Development
Project Manager | Karan Malhotra
Start Date | 01-Jan-2024
End Date | 30-Jun-2024
Department | Business Intelligence / Analytics
Priority | HIGH
Budget (₹) | ₹8,50,000
Status | In Progress
Project Sponsor | Ananya Singh — Senior Analytics Lead
Document Ver. | v1.0 — Professional Reference
KEY PROJECT METRICS
Total Techniques | Completed | In Progress | Not Started | Overall Progress
10 | 5 | 2 | 3 | 50%
QUICK NAVIGATION — CLICK TO JUMP TO ANY SHEET
Sheet Name | Type | Description | [7 empty] | Click to Open
Raw Data (153 rows) | DATA | ⚠ 150 uncleaned records — messy names, dates, revenue & formats | [7 empty] | → Open Raw Data (150 rows)
Cleaned Data (153 rows) | DATA | ✔ 150 standardised & validated records with cleaning flags | [7 empty] | → Open Cleaned Data (150 rows)
Gantt Chart | PLAN | 📅 Full 26-week Gantt across 4 phases with colour-coded bars | [7 empty] | → Open Gantt Chart
Resource Planner | TEAM | 👥 7-person team: allocation, utilisation & workload by phase | [7 empty] | → Open Resource Planner
Task Tracker | TRACK | ✅ Detailed task log with formulas, dependencies & review dates | [7 empty] | → Open Task Tracker
Data Reference | REF | 📖 Before/after raw→clean examples for all 10 techniques | [7 empty] | → Open Data Reference
Formula Cheat Sheet | REF | 🔢 20 key cleaning formulas with syntax, notes & technique map | [7 empty] | → Open Formula Cheat Sheet
Dashboard Checklist | QA | 📋 10-point pre-deployment quality gate with status tracking | [7 empty] | → Open Dashboard Checklist
10 DATA CLEANING TECHNIQUES — OVERVIEW
No. | Technique | Problem Solved |  |  | ▶ Live Formula (click me!) | Sample Input | Phase | Priority | Status
1 | Remove Duplicates — CRM Export Cleaning | CRM Export Cleaning |  |  | FALSE | ORD-1001 | Phase 1 | Critical | Completed
2 | Trim Extra Spaces — Customer Name Import | Customer Name Import |  |  | Priya Sharma | Priya Sharma | Phase 1 | Critical | Completed
3 | Standardize Text Case — Region Codes | Region Codes |  |  | North West | north west | Phase 1 | High | Completed
4 | Fix Date Formats — Legacy System Dates | Legacy System Dates |  |  | 45320 | 2024-01-29 | Phase 2 | Critical | Completed
5 | Handle Missing Values — Customer Database | Customer Database |  |  | Unknown |  | Phase 2 | High | Completed
6 | Split Combined Columns — Contact Database | Contact Database |  |  | Karan | Karan Malhotra | Phase 2 | Medium | In Progress
7 | Remove Non-Numeric Chars — Revenue Data | Revenue Data |  |  | 150000 | Rs. 1,50,000 | Phase 3 | Critical | In Progress
8 | Validate Data Ranges — HR Age Dataset | HR Age Dataset |  |  | Valid | 45 | Phase 3 | High | Not Started
9 | Standardize Category Labels — Product SKU | Product SKU |  |  | Electronics | electronics | Phase 3 | High | Not Started
10 | Combine & Reconcile Columns — Address | Address |  |  | 123 Main St, Mumbai, 400001 | 123 Main St | Phase 4 | Medium | Not Started

## Raw Data
⚠ RAW DATA — 153 Records (Uncleaned) ¦ Project Management Dashboard
← Back to Project Overview
# | Task / Technique | Phase | Assigned To | Department | Start Date | End Date | Duration (Days) | Status | % Complete | Priority | Daily Rate (₹) | Hours | Revenue (Raw) | Notes
1 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Sunita Verma | BI & Analytics | 2024-02-06 |  | 10 | Completed | 40 | Low | 3000 | TBD | Rs. 154,716 | —
2 | Trim Extra Spaces — Customer Name Import | PHASE 2 | deepa krishnan | business intel. | 2024-05-15 |  | 14 | not started | 100.00% | LOW | ₹4200 | TBD | Rs.707655 | —
3 | Standardize Text Case — Region Codes | Phase 3 | Amit Roy | DATA PLATFORM | 01/25/2024 |  | 7 | COMPLETED | 25 | high | ₹4200 | 160 | 499533 | —
4 | Fix Date Formats — Legacy System Dates | PHASE4 | neha joshi | QUALITY ASSUR. | 2024-03-17 |  | 10 | Complete | 0 | CRITICAL | ₹2,000 | 80 | ₹511,738 | —
5 | Handle Missing Values — Customer Database | PHASE1 | Deepa Krishnan | PMO | 15-05-2024 |  | 12 | COMPLETED | 100 % | high | INR 5,500 | N/A | ₹586,967 | —
6 | Split Combined Columns — Contact Database | phase 2 | DEEPA KRISHNAN | BI & ANALYTICS | 2024-02-08 |  | 10 | Complete | 25.00% | CRITICAL | Rs. 3,500 | N/A | Rs.444784 | Extra spaces detected
7 | Trim Extra Spaces — Customer Name Import | PHASE 2 | deepa krishnan | business intel. | 2024-05-15 |  | 14 | not started | 100.00% | LOW | ₹4200 | TBD | Rs.707655 | —
8 | Validate Data Ranges — HR Age Dataset | PHASE4 | Siddharth Rao | data platform | 02/18/2024 |  | 28 | In-Progress | 100.00% | Low | Rs. 4,000 | 120 | Rs. 340,746 | —
9 | Standardize Category Labels — Product SKU | PHASE 1 | Meera Pillai | Quality Assur. | 15-03-2024 |  | 21 | Complete | 50.00% | low | Rs.5000 |  | INR 148,463 | Re-run TRIM
10 | Combine & Reconcile Columns — Address | PHASE2 | Rohit Gupta | pmo | 2024-01-19 |  | 12 | NOT STARTED | 75.00% | medium | Rs. 3,500 | 120 | INR 19,520 | —
11 | Remove Duplicates — CRM Export Cleaning | PHASE 3 | Meera Pillai | BI & Analytics | 2024-05-07 |  | 7 | NOT STARTED | 25% | Low | 3000 | 140 | 541024 | Awaiting sign-off
12 | Trim Extra Spaces — Customer Name Import | PHASE 4 | Lakshmi Nair | BUSINESS INTEL. | 2024-04-22 |  | 12 | in progress | 0% | Medium | Rs.5000 | 140 | 94242 | Check formula
13 | Standardize Text Case — Region Codes | PHASE1 | Priya Sharma | data platform | 22-02-2024 |  | 10 | NOT STARTED | 100 | MEDIUM | Rs.5000 | TBD | ₹152,010 | Needs validation
14 | Fix Date Formats — Legacy System Dates | Phase 2 | Priya Sharma | QUALITY ASSUR. | 01/27/2024 |  | 28 | completed | 0 % | MEDIUM | Rs.5000 | TBD | Rs.514492 | Check formula
15 | Handle Missing Values — Customer Database | PHASE 3 | RAHUL MEHTA | PMO | 02/20/2024 |  | 12 | in progress | 25 % | CRITICAL | 3000 | 60 | INR 449,046 | Verified OK
16 | Split Combined Columns — Contact Database | Phase 4 | Rahul Mehta | BI & ANALYTICS | 2024-03-11 |  | 10 | Completed | 25.00% | high | INR 5,500 | 160 | ₹137,858 | Extra spaces detected
17 | Remove Non-Numeric Chars — Revenue Data | phase 1 | SUNITA VERMA | Business Intel. | 2024-01-21 |  | 10 | NOT STARTED | 0 | HIGH | Rs. 4,000 | 160 | Rs. 586,812 | Pending review
18 | Validate Data Ranges — HR Age Dataset | PHASE2 | Vikram Nair | data platform | 02/06/2024 |  | 7 | not started | 75% | high | Rs. 4,000 | 168 | ₹168,685 | —
19 | Standardize Category Labels — Product SKU | PHASE3 | NEHA JOSHI | QUALITY ASSUR. | 18-04-2024 |  | 12 | COMPLETED | 0 | CRITICAL | ₹4200 | 140 | 343619 | Verified OK
20 | Combine & Reconcile Columns — Address | Phase 4 | Arjun Pillai | PMO | 27-03-2024 |  | 10 | Completed | 100.00% | medium | ₹2,000 | 160 | INR 650,940 | Needs validation
21 | Remove Duplicates — CRM Export Cleaning | phase 1 | pooja iyer | bi & analytics | 07-05-2024 |  | 21 | Complete | 25 | high | ₹4200 | 120 | Rs.765374 | Check formula
22 | Trim Extra Spaces — Customer Name Import | phase 2 | POOJA IYER | BUSINESS INTEL. | 2024-02-22 |  | 28 | completed | 40 % | critical | 3000 | 168 | Rs. 330,067 | —
23 | Split Combined Columns — Contact Database | phase 2 | DEEPA KRISHNAN | BI & ANALYTICS | 2024-02-08 |  | 10 | Complete | 25.00% | CRITICAL | Rs. 3,500 | N/A | Rs.444784 | Extra spaces detected
24 | Fix Date Formats — Legacy System Dates | PHASE4 | Karan Malhotra | QUALITY ASSUR. | 23-03-2024 |  | 28 | Not Started | 100.00% | Critical | Rs. 4,000 | TBD | Rs.275487 | Needs validation
25 | Handle Missing Values — Customer Database | Phase 1 | rohit gupta | pmo | 01/11/2024 |  | 7 | completed | 40.00% | CRITICAL | Rs.5000 | 120 | INR 268,358 | Pending review
26 | Split Combined Columns — Contact Database | phase 2 | ananya singh | BI & Analytics | 2024-01-07 |  | 12 | COMPLETED | 0.00% | MEDIUM | Rs. 4,000 | 160 | INR 719,497 | Extra spaces detected
27 | Remove Non-Numeric Chars — Revenue Data | phase 3 | Rohit Gupta | BUSINESS INTEL. | 2024-05-23 |  | 10 | In Progress | 100 | high | ₹4200 | 160 | Rs. 652,813 | Extra spaces detected
28 | Validate Data Ranges — HR Age Dataset | phase 4 | ANANYA SINGH | DATA PLATFORM | 2024-05-15 |  | 12 | in progress | 100% | Low | ₹2,000 | 60 | INR 665,883 | Flag for QA
29 | Standardize Category Labels — Product SKU | Phase 1 | Priya Sharma | Quality Assur. | 05/01/2024 |  | 28 | in progress | 75.00% | High | Rs. 3,500 | 80 | INR 290,590 | Pending review
30 | Combine & Reconcile Columns — Address | phase 2 | Priya Sharma | pmo | 05/11/2024 |  | 21 | Not_Started | 50 | CRITICAL | 3000 | 60 | Rs.269913 | Check formula
31 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Priya Sharma | bi & analytics | 03/15/2024 |  | 10 | completed | 100% | MEDIUM | INR 5,500 | 168 | 649359 | Flag for QA
32 | Trim Extra Spaces — Customer Name Import | phase 4 | Vikram Nair | Business Intel. | 2024-04-22 |  | 21 | Not Started | 100 | Critical | Rs. 4,000 | 168 | Rs.102675 | Check formula
33 | Standardize Text Case — Region Codes | PHASE1 | vikram nair | Data Platform | 2024-02-16 |  | 14 | Completed | 25 % | CRITICAL | Rs. 3,500 | 140 | INR 885,691 | Extra spaces detected
34 | Fix Date Formats — Legacy System Dates | phase 2 | Arjun Pillai | QUALITY ASSUR. | 01/01/2024 |  | 12 | Completed | 100.00% | CRITICAL | ₹2,000 | 80 | Rs.277344 | —
35 | Handle Missing Values — Customer Database | PHASE 3 | neha joshi | PMO | 2024-02-28 |  | 21 | In-Progress | 40.00% | High | ₹2,000 | 100 | ₹336,526 | —
36 | Split Combined Columns — Contact Database | PHASE4 | pooja iyer | BI & Analytics | 05/23/2024 |  | 21 | not started | 65 | medium | Rs. 3,500 | 100 | Rs.89000 | Flag for QA
37 | Remove Non-Numeric Chars — Revenue Data | phase 1 | POOJA IYER | business intel. | 11-03-2024 |  | 14 | Complete | 0 % | High | Rs. 3,500 | 80 | Rs. 126,838 | Extra spaces detected
38 | Validate Data Ranges — HR Age Dataset | PHASE2 | Pooja Iyer | DATA PLATFORM | 17-03-2024 |  | 7 | In-Progress | 50.00% | low | 3000 | 60 | INR 243,606 | Minor inconsistency
39 | Standardize Category Labels — Product SKU | PHASE 3 | siddharth rao | QUALITY ASSUR. | 04/28/2024 |  | 12 | Not Started | 75 % | low | Rs. 3,500 | 120 | 744557 | —
40 | Combine & Reconcile Columns — Address | PHASE 4 | Siddharth Rao | PMO | 03/21/2024 |  | 21 | Not_Started | 25 | MEDIUM | ₹4200 | 80 | Rs.375752 | Extra spaces detected
41 | Remove Duplicates — CRM Export Cleaning | phase 1 | Lakshmi Nair | BI & Analytics | 17-01-2024 |  | 7 | COMPLETED | 50 % | CRITICAL | ₹2,000 | 100 | INR 715,402 | —
42 | Trim Extra Spaces — Customer Name Import | PHASE 2 | Lakshmi Nair | Business Intel. | 01-05-2024 |  | 7 | Complete | 25% | LOW | INR 5,500 | 80 | INR 228,678 | Minor inconsistency
43 | Standardize Text Case — Region Codes | PHASE 3 | ROHIT GUPTA | data platform | 2024-01-09 |  | 10 | Not_Started | 40% | High | 3000 | TBD | Rs.714390 | —
44 | Fix Date Formats — Legacy System Dates | PHASE 4 | amit roy | quality assur. | 02/16/2024 |  | 14 | not started | 0 | LOW | Rs. 4,000 | N/A | INR 111,961 | Needs validation
45 | Handle Missing Values — Customer Database | PHASE1 | SUNITA VERMA | pmo | 06-04-2024 |  | 21 | completed | 100% | Low | ₹4200 | 60 | INR 150,227 | Re-run TRIM
46 | Split Combined Columns — Contact Database | Phase 2 | Vikram Nair | BI & Analytics | 2024-05-17 |  | 28 | COMPLETED | 25 % | LOW | ₹2,000 | 168 | 61837 | Minor inconsistency
47 | Remove Non-Numeric Chars — Revenue Data | PHASE 3 | RAHUL MEHTA | BUSINESS INTEL. | 01/25/2024 |  | 10 | Complete | 100.00% | medium | Rs. 3,500 | N/A | ₹612,246 | Extra spaces detected
48 | Validate Data Ranges — HR Age Dataset | PHASE 4 | Amit Roy | Data Platform | 02/12/2024 |  | 14 | In Progress | 25.00% | medium | Rs.5000 | 80 | INR 724,521 | Awaiting sign-off
49 | Standardize Category Labels — Product SKU | PHASE1 | ARJUN PILLAI | QUALITY ASSUR. | 2024-03-25 |  | 10 | In Progress | 25 % | MEDIUM | INR 5,500 | 140 | Rs. 722,090 | Extra spaces detected
50 | Combine & Reconcile Columns — Address | phase 2 | Arjun Pillai | PMO | 17-01-2024 |  | 14 | in progress | 75.00% | high | ₹2,000 | 100 | ₹306,112 | Minor inconsistency
51 | Remove Duplicates — CRM Export Cleaning | PHASE3 | Deepa Krishnan | bi & analytics | 05/15/2024 |  | 7 | IN PROGRESS | 40 | Critical | 3000 | 160 | ₹846,911 | Needs validation
52 | Trim Extra Spaces — Customer Name Import | PHASE4 | Neha Joshi | BUSINESS INTEL. | 2024-01-09 |  | 12 | IN PROGRESS | 0% | MEDIUM | ₹4200 | N/A | Rs.99642 | —
53 | Standardize Text Case — Region Codes | PHASE1 | MEERA PILLAI | Data Platform | 03/19/2024 |  | 14 | NOT STARTED | 40.00% | low | ₹2,000 | 100 | ₹640,427 | —
54 | Fix Date Formats — Legacy System Dates | Phase 2 | Pooja Iyer | quality assur. | 07-03-2024 |  | 28 | Not Started | 65.00% | CRITICAL | 3000 | N/A | ₹558,878 | Pending review
55 | Handle Missing Values — Customer Database | phase 3 | ananya singh | pmo | 2024-04-02 |  | 14 | completed | 100% | low | ₹2,000 | 120 | INR 472,147 | Pending review
56 | Split Combined Columns — Contact Database | PHASE4 | siddharth rao | BI & ANALYTICS | 17-01-2024 |  | 7 | Completed | 0 % | High | ₹4200 | 120 | Rs. 377,724 | Verified OK
57 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | meera pillai | business intel. | 26-06-2024 |  | 12 | COMPLETED | 25.00% | Critical | ₹4200 | N/A | INR 378,614 | —
58 | Validate Data Ranges — HR Age Dataset | Phase 2 | Lakshmi Nair | data platform | 04/10/2024 |  | 14 | Not Started | 0 | CRITICAL | ₹4200 | 140 | ₹694,824 | Check formula
59 | Standardize Category Labels — Product SKU | PHASE 3 | Rohit Gupta | Quality Assur. | 2024-05-17 |  | 12 | In-Progress | 65.00% | Low | ₹2,000 | 140 | INR 391,378 | Minor inconsistency
60 | Combine & Reconcile Columns — Address | phase 4 | Priya Sharma | PMO | 2024-02-28 |  | 7 | COMPLETED | 0.00% | Critical | Rs.5000 | 160 | Rs.728925 | Verified OK
61 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Amit Roy | BI & Analytics | 18-06-2024 |  | 12 | Completed | 40 | critical | ₹2,000 | 100 | ₹214,929 | Pending review
62 | Trim Extra Spaces — Customer Name Import | PHASE 2 | AMIT ROY | business intel. | 2024-05-25 |  | 7 | Complete | 75.00% | High | 3000 | 140 | INR 158,540 | Needs validation
63 | Standardize Text Case — Region Codes | phase 3 | Vikram Nair | Data Platform | 02/10/2024 |  | 10 | In-Progress | 75 % | high | INR 5,500 | N/A | 16054 | Needs validation
64 | Fix Date Formats — Legacy System Dates | Phase 4 | Vikram Nair | quality assur. | 2024-03-11 |  | 14 | In Progress | 65% | High | ₹2,000 | 120 | INR 252,731 | Verified OK
65 | Handle Missing Values — Customer Database | phase 1 | vikram nair | PMO | 02-02-2024 |  | 7 | completed | 25% | Critical | Rs. 4,000 | 80 | Rs. 89,115 | Pending review
66 | Split Combined Columns — Contact Database | PHASE2 | Neha Joshi | bi & analytics | 01/03/2024 |  | 7 | in progress | 50 % | Medium | 3000 | N/A | Rs.464161 | Flag for QA
67 | Remove Non-Numeric Chars — Revenue Data | PHASE3 | Karan Malhotra | Business Intel. | 2024-02-12 |  | 21 | Complete | 75 % | low | 3000 | N/A | INR 593,245 | Needs validation
68 | Validate Data Ranges — HR Age Dataset | PHASE4 | NEHA JOSHI | data platform | 2024-05-19 |  | 10 | Not_Started | 75 | Critical | Rs. 3,500 | 80 | Rs.151703 | Needs validation
69 | Standardize Category Labels — Product SKU | Phase 1 | ANANYA SINGH | Quality Assur. | 01/21/2024 |  | 12 | Not Started | 40 | MEDIUM | Rs. 4,000 | TBD | 795227 | Needs validation
70 | Combine & Reconcile Columns — Address | PHASE2 | ROHIT GUPTA | PMO | 2024-04-06 |  | 21 | Complete | 25 | Low | Rs. 3,500 | 140 | 261943 | Re-run TRIM
71 | Remove Duplicates — CRM Export Cleaning | phase 3 | ANANYA SINGH | BI & Analytics | 01/11/2024 |  | 28 | in progress | 25 % | Low | ₹2,000 | N/A | INR 279,307 | —
72 | Trim Extra Spaces — Customer Name Import | PHASE4 | rohit gupta | Business Intel. | 04-04-2024 |  | 10 | Not Started | 65% | HIGH | ₹2,000 | N/A | 655855 | Awaiting sign-off
73 | Standardize Text Case — Region Codes | PHASE1 | Lakshmi Nair | DATA PLATFORM | 2024-04-10 |  | 21 | Completed | 0.00% | medium | ₹4200 | 168 | INR 496,586 | Check formula
74 | Fix Date Formats — Legacy System Dates | PHASE2 | Lakshmi Nair | Quality Assur. | 2024-04-28 |  | 10 | Not Started | 100% | medium | Rs.5000 | 80 | Rs. 882,832 | Verified OK
75 | Handle Missing Values — Customer Database | phase 3 | Amit Roy | PMO | 10-02-2024 |  | 21 | completed | 40 % | Critical | INR 5,500 | 160 | 631362 | Flag for QA
76 | Split Combined Columns — Contact Database | PHASE4 | Rahul Mehta | BI & ANALYTICS | 21-05-2024 |  | 7 | not started | 50 | High | Rs. 3,500 | 140 | Rs.339019 | Minor inconsistency
77 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | RAHUL MEHTA | BUSINESS INTEL. | 13-03-2024 |  | 28 | completed | 25 | MEDIUM | INR 5,500 | 80 | Rs.668837 | Extra spaces detected
78 | Validate Data Ranges — HR Age Dataset | phase 2 | SUNITA VERMA | data platform | 02/24/2024 |  | 12 | Not Started | 100.00% | medium | 3000 | 168 | Rs.511189 | Extra spaces detected
79 | Standardize Category Labels — Product SKU | PHASE3 | arjun pillai | QUALITY ASSUR. | 09-01-2024 |  | 14 | Not Started | 75 | Critical | INR 5,500 | 80 | INR 279,905 | —
80 | Combine & Reconcile Columns — Address | Phase 4 | KARAN MALHOTRA | PMO | 06/14/2024 |  | 7 | in progress | 0 | High | 3000 | 168 | Rs.722246 | Check formula
81 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Arjun Pillai | BI & ANALYTICS | 18-02-2024 |  | 14 | Not Started | 75% | Critical | 3000 |  | INR 696,775 | —
82 | Trim Extra Spaces — Customer Name Import | PHASE2 | Siddharth Rao | BUSINESS INTEL. | 01/13/2024 |  | 12 | In Progress | 40% | medium | Rs. 4,000 | N/A | INR 219,415 | —
83 | Standardize Text Case — Region Codes | phase 3 | KARAN MALHOTRA | Data Platform | 2024-04-08 |  | 21 | not started | 65.00% | Low | Rs.5000 | 60 | INR 794,492 | Extra spaces detected
84 | Fix Date Formats — Legacy System Dates | PHASE 4 | Siddharth Rao | QUALITY ASSUR. | 06/10/2024 |  | 12 | not started | 65 | low | ₹4200 | 120 | ₹614,503 | Extra spaces detected
85 | Handle Missing Values — Customer Database | Phase 1 | siddharth rao | pmo | 19-05-2024 |  | 21 | Completed | 75 % | High | ₹4200 | TBD | ₹130,300 | Awaiting sign-off
86 | Split Combined Columns — Contact Database | phase 2 | meera pillai | bi & analytics | 04-04-2024 |  | 14 | Completed | 50 | low | 3000 | 140 | Rs.862527 | Flag for QA
87 | Remove Non-Numeric Chars — Revenue Data | PHASE3 | Meera Pillai | business intel. | 2024-01-19 |  | 28 | In Progress | 65% | Medium | INR 5,500 | TBD | ₹154,188 | Flag for QA
88 | Validate Data Ranges — HR Age Dataset | PHASE4 | Ananya Singh | Data Platform | 2024-05-25 |  | 7 | IN PROGRESS | 50% | Critical | INR 5,500 | 140 | INR 587,064 | Re-run TRIM
89 | Standardize Category Labels — Product SKU | phase 1 | Rohit Gupta | Quality Assur. | 02/16/2024 |  | 7 | NOT STARTED | 0 | medium | Rs. 4,000 | 100 | 330852 | Check formula
90 | Combine & Reconcile Columns — Address | Phase 2 | Rahul Mehta | PMO | 05/15/2024 |  | 14 | not started | 40.00% | Critical | Rs. 3,500 | N/A | Rs.740603 | Minor inconsistency
91 | Remove Duplicates — CRM Export Cleaning | PHASE3 | PRIYA SHARMA | bi & analytics | 07-03-2024 |  | 21 | COMPLETED | 75 | low | ₹2,000 | N/A | 242510 | —
92 | Trim Extra Spaces — Customer Name Import | phase 4 | Sunita Verma | BUSINESS INTEL. | 2024-05-27 |  | 12 | Completed | 25.00% | Critical | INR 5,500 | 80 | INR 428,130 | —
93 | Standardize Text Case — Region Codes | PHASE1 | Arjun Pillai | DATA PLATFORM | 03/19/2024 |  | 14 | in progress | 0% | LOW | ₹2,000 | 60 | Rs.195412 | Awaiting sign-off
94 | Fix Date Formats — Legacy System Dates | PHASE2 | deepa krishnan | quality assur. | 02/24/2024 |  | 21 | completed | 100% | critical | INR 5,500 | 60 | Rs.302207 | Re-run TRIM
95 | Handle Missing Values — Customer Database | Phase 3 | KARAN MALHOTRA | PMO | 02/18/2024 |  | 21 | Not Started | 75 % | HIGH | INR 5,500 | N/A | 106907 | —
96 | Split Combined Columns — Contact Database | PHASE 4 | Arjun Pillai | bi & analytics | 21-01-2024 |  | 12 | Not Started | 65 % | HIGH | ₹2,000 | N/A | 529551 | Needs validation
97 | Remove Non-Numeric Chars — Revenue Data | PHASE 1 | Siddharth Rao | business intel. | 10-06-2024 |  | 12 | Complete | 25.00% | CRITICAL | Rs. 4,000 | 140 | INR 334,691 | —
98 | Validate Data Ranges — HR Age Dataset | Phase 2 | meera pillai | DATA PLATFORM | 2024-05-07 |  | 14 | Completed | 65 | low | Rs. 4,000 | 60 | ₹116,177 | Verified OK
99 | Standardize Category Labels — Product SKU | phase 3 | ananya singh | QUALITY ASSUR. | 03-01-2024 |  | 14 | Not_Started | 65.00% | Low | Rs. 4,000 | 140 | Rs.562835 | Check formula
100 | Combine & Reconcile Columns — Address | PHASE4 | Pooja Iyer | PMO | 2024-02-18 |  | 28 | Complete | 25 % | High | ₹2,000 | 160 | Rs. 674,247 | —
101 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Ananya Singh | BI & Analytics | 02/26/2024 |  | 12 | not started | 40.00% | low | Rs.5000 | 140 | Rs.440201 | Check formula
102 | Trim Extra Spaces — Customer Name Import | Phase 2 | ROHIT GUPTA | Business Intel. | 15-01-2024 |  | 10 | Completed | 50.00% | LOW | ₹4200 | 168 | ₹208,648 | —
103 | Standardize Text Case — Region Codes | PHASE3 | Priya Sharma | Data Platform | 28-02-2024 |  | 7 | Completed | 75 % | Low | Rs.5000 | 140 | 141339 | Pending review
104 | Fix Date Formats — Legacy System Dates | phase 4 | Amit Roy | Quality Assur. | 2024-06-18 |  | 14 | Completed | 65.00% | HIGH | ₹2,000 | 168 | INR 410,161 | Check formula
105 | Handle Missing Values — Customer Database | PHASE1 | Amit Roy | PMO | 04-02-2024 |  | 7 | Completed | 0% | CRITICAL | Rs.5000 | 100 | Rs. 287,972 | Needs validation
106 | Split Combined Columns — Contact Database | PHASE 2 | Rahul Mehta | BI & Analytics | 05/19/2024 |  | 12 | in progress | 0.00% | CRITICAL | ₹2,000 | 100 | Rs. 759,941 | —
107 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | deepa krishnan | BUSINESS INTEL. | 2024-03-17 |  | 14 | IN PROGRESS | 75% | MEDIUM | Rs. 3,500 | N/A | Rs.297337 | Pending review
108 | Validate Data Ranges — HR Age Dataset | Phase 4 | Sunita Verma | DATA PLATFORM | 01/03/2024 |  | 21 | not started | 100.00% | Critical | ₹2,000 |  | Rs. 745,912 | —
109 | Standardize Category Labels — Product SKU | PHASE 1 | Deepa Krishnan | QUALITY ASSUR. | 2024-06-14 |  | 28 | Complete | 75.00% | low | Rs. 4,000 | TBD | ₹703,773 | Flag for QA
110 | Combine & Reconcile Columns — Address | PHASE2 | KARAN MALHOTRA | PMO | 28-02-2024 |  | 12 | Not Started | 0 | LOW | 3000 | 100 | INR 755,543 | Needs validation
111 | Remove Duplicates — CRM Export Cleaning | PHASE 3 | deepa krishnan | bi & analytics | 12-02-2024 |  | 21 | Complete | 25.00% | high | Rs.5000 | 60 | Rs. 614,949 | Re-run TRIM
112 | Trim Extra Spaces — Customer Name Import | Phase 4 | Neha Joshi | Business Intel. | 2024-04-12 |  | 21 | COMPLETED | 100.00% | critical | Rs. 4,000 | 60 | 852136 | —
113 | Standardize Text Case — Region Codes | PHASE1 | Neha Joshi | data platform | 2024-01-09 |  | 14 | NOT STARTED | 100 % | LOW | Rs.5000 | 80 | Rs. 241,765 | Needs validation
114 | Fix Date Formats — Legacy System Dates | PHASE2 | Meera Pillai | Quality Assur. | 2024-01-27 |  | 7 | Complete | 50.00% | critical | ₹4200 |  | INR 737,645 | Flag for QA
115 | Handle Missing Values — Customer Database | PHASE3 | Siddharth Rao | PMO | 10-02-2024 |  | 10 | in progress | 25% | Low | Rs. 4,000 | TBD | ₹571,755 | Minor inconsistency
116 | Split Combined Columns — Contact Database | phase 4 | Ananya Singh | BI & ANALYTICS | 17-05-2024 |  | 7 | Completed | 50.00% | LOW | Rs. 4,000 | 168 | ₹796,423 | Check formula
117 | Remove Non-Numeric Chars — Revenue Data | PHASE1 | ROHIT GUPTA | BUSINESS INTEL. | 03/05/2024 |  | 28 | Complete | 40.00% | Critical | 3000 | 160 | Rs.642962 | Verified OK
118 | Validate Data Ranges — HR Age Dataset | phase 2 | rohit gupta | DATA PLATFORM | 01-01-2024 |  | 21 | NOT STARTED | 25 | medium | ₹2,000 | N/A | ₹709,825 | Re-run TRIM
119 | Standardize Category Labels — Product SKU | phase 3 | PRIYA SHARMA | QUALITY ASSUR. | 15-05-2024 |  | 14 | in progress | 100.00% | MEDIUM | ₹4200 | 168 | 779849 | Flag for QA
120 | Combine & Reconcile Columns — Address | Phase 4 | Lakshmi Nair | PMO | 28-06-2024 |  | 12 | In Progress | 100.00% | High | INR 5,500 |  | Rs.30394 | —
121 | Remove Duplicates — CRM Export Cleaning | PHASE 1 | SUNITA VERMA | bi & analytics | 2024-03-17 |  | 21 | completed | 50 % | Medium | ₹2,000 | 60 | INR 379,501 | —
122 | Trim Extra Spaces — Customer Name Import | PHASE 2 | Rahul Mehta | BUSINESS INTEL. | 26-02-2024 |  | 10 | Not Started | 40 | Medium | ₹4200 | N/A | 296464 | —
123 | Standardize Text Case — Region Codes | PHASE3 | ARJUN PILLAI | Data Platform | 01-05-2024 |  | 14 | NOT STARTED | 25% | medium | Rs.5000 | 60 | Rs. 186,651 | Verified OK
124 | Fix Date Formats — Legacy System Dates | phase 4 | SUNITA VERMA | quality assur. | 01/13/2024 |  | 10 | Complete | 40 % | low | Rs. 3,500 |  | Rs.759798 | Flag for QA
125 | Handle Missing Values — Customer Database | phase 1 | vikram nair | PMO | 2024-06-26 |  | 12 | Completed | 75 % | CRITICAL | ₹4200 | 168 | Rs. 883,335 | —
126 | Split Combined Columns — Contact Database | phase 2 | Deepa Krishnan | bi & analytics | 2024-05-13 |  | 14 | COMPLETED | 25 % | CRITICAL | Rs. 3,500 | 160 | ₹123,551 | Verified OK
127 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | neha joshi | Business Intel. | 05/25/2024 |  | 28 | Complete | 65.00% | LOW | 3000 | 120 | Rs. 42,667 | Flag for QA
128 | Validate Data Ranges — HR Age Dataset | phase 4 | KARAN MALHOTRA | Data Platform | 2024-03-27 |  | 12 | In-Progress | 75.00% | Critical | ₹2,000 | TBD | Rs.880473 | Needs validation
129 | Standardize Category Labels — Product SKU | PHASE 1 | karan malhotra | QUALITY ASSUR. | 04/20/2024 |  | 21 | in progress | 75 % | MEDIUM | Rs.5000 | N/A | Rs. 591,699 | —
130 | Combine & Reconcile Columns — Address | Phase 2 | Meera Pillai | PMO | 01/19/2024 |  | 12 | Not Started | 25.00% | CRITICAL | Rs. 3,500 |  | Rs.637287 | Awaiting sign-off
131 | Remove Duplicates — CRM Export Cleaning | phase 3 | Rohit Gupta | BI & ANALYTICS | 2024-05-25 |  | 14 | In Progress | 75 | LOW | 3000 | 140 | Rs.595811 | Flag for QA
132 | Trim Extra Spaces — Customer Name Import | PHASE4 | rohit gupta | BUSINESS INTEL. | 14-04-2024 |  | 21 | Completed | 65 % | LOW | Rs.5000 | 80 | 505134 | Check formula
133 | Standardize Text Case — Region Codes | Phase 1 | RAHUL MEHTA | Data Platform | 06/08/2024 |  | 28 | Complete | 65 | critical | ₹4200 |  | ₹593,997 | Verified OK
134 | Fix Date Formats — Legacy System Dates | PHASE 2 | Lakshmi Nair | QUALITY ASSUR. | 04/22/2024 |  | 10 | In Progress | 50 % | high | 3000 | 160 | Rs.767173 | Check formula
135 | Handle Missing Values — Customer Database | Phase 3 | Lakshmi Nair | pmo | 2024-06-06 |  | 7 | completed | 25% | Medium | INR 5,500 | 160 | INR 460,655 | Verified OK
136 | Split Combined Columns — Contact Database | phase 4 | Sunita Verma | bi & analytics | 03/07/2024 |  | 10 | in progress | 50% | HIGH | Rs. 4,000 | 80 | ₹134,327 | Verified OK
137 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Sunita Verma | business intel. | 26-02-2024 |  | 10 | NOT STARTED | 50% | MEDIUM | Rs. 4,000 | TBD | Rs.121689 | —
138 | Validate Data Ranges — HR Age Dataset | Phase 2 | Sunita Verma | data platform | 2024-02-14 |  | 12 | in progress | 50% | HIGH | ₹2,000 | 100 | Rs. 275,808 | —
139 | Standardize Category Labels — Product SKU | phase 3 | Neha Joshi | Quality Assur. | 14-04-2024 |  | 7 | COMPLETED | 25% | medium | 3000 |  | Rs.845321 | Awaiting sign-off
140 | Combine & Reconcile Columns — Address | PHASE 4 | Karan Malhotra | pmo | 2024-01-21 |  | 28 | Not Started | 65 % | critical | Rs. 3,500 | 140 | Rs.536688 | —
141 | Remove Duplicates — CRM Export Cleaning | PHASE1 | POOJA IYER | BI & ANALYTICS | 02-04-2024 |  | 28 | Completed | 40 % | high | 3000 | 168 | 564399 | Pending review
142 | Trim Extra Spaces — Customer Name Import | phase 2 | siddharth rao | BUSINESS INTEL. | 2024-04-22 |  | 14 | completed | 100 | Critical | ₹2,000 | 80 | ₹226,560 | —
143 | Standardize Text Case — Region Codes | Phase 3 | Meera Pillai | data platform | 18-06-2024 |  | 21 | completed | 50 | medium | INR 5,500 | 60 | 282169 | —
144 | Fix Date Formats — Legacy System Dates | Phase 4 | ANANYA SINGH | Quality Assur. | 03/25/2024 |  | 21 | COMPLETED | 75% | low | 3000 |  | Rs.155947 | Check formula
145 | Handle Missing Values — Customer Database | PHASE 1 | Rohit Gupta | pmo | 04/18/2024 |  | 10 | Completed | 25% | low | Rs. 3,500 | 160 | Rs. 809,899 | —
146 | Split Combined Columns — Contact Database | PHASE2 | Lakshmi Nair | bi & analytics | 27-03-2024 |  | 12 | Completed | 75 % | critical | Rs. 3,500 | 100 | Rs. 209,704 | Verified OK
147 | Remove Non-Numeric Chars — Revenue Data | phase 3 | Meera Pillai | Business Intel. | 04/20/2024 |  | 28 | in progress | 75% | Medium | ₹2,000 | TBD | Rs. 866,996 | —
148 | Validate Data Ranges — HR Age Dataset | PHASE 4 | ROHIT GUPTA | Data Platform | 01/25/2024 |  | 12 | NOT STARTED | 100 | low | Rs. 4,000 |  | Rs.760636 | Re-run TRIM
149 | Standardize Category Labels — Product SKU | Phase 1 | rohit gupta | QUALITY ASSUR. | 27-03-2024 |  | 12 | in progress | 0 % | Low | ₹4200 | N/A | INR 249,341 | Pending review
150 | Combine & Reconcile Columns — Address | phase 2 | lakshmi nair | pmo | 2024-06-18 |  | 7 | Not Started | 0 | HIGH | ₹2,000 | 60 | 399153 | Needs validation

## Cleaned Data
✔ CLEANED DATA — 153 Records (Standardised & Validated) ¦ Project Management Dashboard
← Back to Project Overview
# | Task / Technique | Phase | Assigned To | Department | Start Date | End Date | Duration (Days) | Status | % Complete | Priority | Daily Rate (₹) | Hours | Revenue (₹) | Notes | Flag
1 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Rahul Mehta | BI & Analytics | 2024-03-24 | 2024-04-03 | 10 | Completed | 100% | High | 2000 | 140 | 529370 | Extra spaces detected | Status, Priority
2 | Trim Extra Spaces — Customer Name Import | Phase 2 | Sunita Verma | Business Intel. | 2024-05-08 | 2024-05-15 | 7 | In Progress | 100% | Critical | 4000 | 100 | 860932 | Extra spaces detected | —
3 | Standardize Text Case — Region Codes | Phase 3 | Sunita Verma | Data Platform | 2024-02-16 | 2024-02-28 | 12 | In Progress | 0% | Critical | 4200 | 140 | 589906 | — | Status, Priority
4 | Fix Date Formats — Legacy System Dates | Phase 4 | Sunita Verma | Quality Assur. | 2024-02-19 | 2024-02-26 | 7 | Completed | 75% | High | 4200 | 0 | 654239 | Pending review | Name, Dept
5 | Handle Missing Values — Customer Database | Phase 1 | Arjun Pillai | PMO | 2024-02-24 | 2024-03-23 | 28 | In Progress | 0% | Critical | 4200 | 0 | 113184 | Pending review | Name, Phase
6 | Split Combined Columns — Contact Database | Phase 2 | Arjun Pillai | BI & Analytics | 2024-05-21 | 2024-05-28 | 7 | In Progress | 100% | Critical | 5500 | 168 | 817541 | Extra spaces detected | Status, Priority
7 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Karan Malhotra | Business Intel. | 2024-04-30 | 2024-05-14 | 14 | Not Started | 100% | High | 5500 | 168 | 43413 | — | Name, Dept
8 | Validate Data Ranges — HR Age Dataset | Phase 4 | Karan Malhotra | Data Platform | 2024-01-11 | 2024-02-08 | 28 | In Progress | 0% | Low | 3500 | 0 | 88674 | — | Phase, Priority
9 | Standardize Category Labels — Product SKU | Phase 1 | Siddharth Rao | Quality Assur. | 2024-01-25 | 2024-02-04 | 10 | In Progress | 0% | Critical | 5500 | 0 | 400094 | — | —
10 | Combine & Reconcile Columns — Address | Phase 2 | Pooja Iyer | PMO | 2024-01-16 | 2024-01-30 | 14 | Completed | 75% | Critical | 2000 | 120 | 122449 | — | Name, Dept
11 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Meera Pillai | BI & Analytics | 2024-05-01 | 2024-05-08 | 7 | Completed | 40% | High | 3000 | 80 | 199370 | Check formula | Status, Priority
12 | Fix Date Formats — Legacy System Dates | Phase 4 | Sunita Verma | Quality Assur. | 2024-02-19 | 2024-02-26 | 7 | Completed | 75% | High | 4200 | 0 | 654239 | Pending review | Name, Dept
13 | Standardize Text Case — Region Codes | Phase 1 | Ananya Singh | Data Platform | 2024-04-30 | 2024-05-21 | 21 | In Progress | 65% | Medium | 3500 | 140 | 505778 | Extra spaces detected | Name, Dept
14 | Fix Date Formats — Legacy System Dates | Phase 2 | Priya Sharma | Quality Assur. | 2024-05-04 | 2024-05-11 | 7 | Completed | 75% | Critical | 3000 | 60 | 124309 | Pending review | —
15 | Handle Missing Values — Customer Database | Phase 3 | Lakshmi Nair | PMO | 2024-01-22 | 2024-02-05 | 14 | Completed | 75% | Critical | 4000 | 140 | 512606 | — | —
16 | Split Combined Columns — Contact Database | Phase 4 | Amit Roy | BI & Analytics | 2024-04-12 | 2024-04-22 | 10 | Not Started | 100% | Low | 3500 | 140 | 120324 | Verified OK | Name, Phase
17 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Rahul Mehta | Business Intel. | 2024-03-12 | 2024-03-24 | 12 | Not Started | 75% | Low | 5500 | 168 | 558822 | — | Phase, Priority
18 | Validate Data Ranges — HR Age Dataset | Phase 2 | Sunita Verma | Data Platform | 2024-04-06 | 2024-05-04 | 28 | Not Started | 0% | Medium | 3500 | 80 | 182082 | Check formula | Name, Phase
19 | Standardize Category Labels — Product SKU | Phase 3 | Deepa Krishnan | Quality Assur. | 2024-01-13 | 2024-01-23 | 10 | Not Started | 65% | Critical | 2000 | 80 | 700521 | Check formula | Name, Phase
20 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | PMO | 2024-03-28 | 2024-04-04 | 7 | Not Started | 0% | Low | 5000 | 140 | 112639 | Verified OK | Dept, Status
21 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Neha Joshi | BI & Analytics | 2024-01-02 | 2024-01-09 | 7 | In Progress | 50% | High | 4000 | 80 | 480743 | — | Name, Dept
22 | Trim Extra Spaces — Customer Name Import | Phase 2 | Arjun Pillai | Business Intel. | 2024-04-06 | 2024-04-16 | 10 | Completed | 100% | Medium | 4200 | 140 | 693929 | Check formula | —
23 | Standardize Text Case — Region Codes | Phase 3 | Pooja Iyer | Data Platform | 2024-01-23 | 2024-01-30 | 7 | Completed | 65% | Low | 5000 | 80 | 217008 | — | Status, Priority
24 | Fix Date Formats — Legacy System Dates | Phase 4 | Siddharth Rao | Quality Assur. | 2024-05-25 | 2024-06-22 | 28 | In Progress | 50% | Medium | 3000 | 120 | 539617 | — | —
25 | Handle Missing Values — Customer Database | Phase 1 | Siddharth Rao | PMO | 2024-05-22 | 2024-06-01 | 10 | In Progress | 25% | Critical | 5500 | 140 | 704703 | Verified OK | Name, Phase
26 | Split Combined Columns — Contact Database | Phase 2 | Ananya Singh | BI & Analytics | 2024-04-19 | 2024-04-29 | 10 | Not Started | 100% | Medium | 5000 | 120 | 296565 | Verified OK | Phase, Priority
27 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Meera Pillai | Business Intel. | 2024-02-10 | 2024-02-22 | 12 | Not Started | 100% | High | 3500 | 0 | 336639 | Needs validation | Dept, Status
28 | Validate Data Ranges — HR Age Dataset | Phase 4 | Ananya Singh | Data Platform | 2024-01-25 | 2024-02-08 | 14 | Not Started | 40% | Critical | 3500 | 100 | 39667 | Needs validation | —
29 | Standardize Category Labels — Product SKU | Phase 1 | Lakshmi Nair | Quality Assur. | 2024-04-20 | 2024-05-11 | 21 | Not Started | 75% | Low | 4000 | 80 | 750418 | — | Phase, Priority
30 | Combine & Reconcile Columns — Address | Phase 2 | Rahul Mehta | PMO | 2024-04-01 | 2024-04-15 | 14 | In Progress | 25% | Low | 4000 | 168 | 611124 | — | —
31 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Rahul Mehta | BI & Analytics | 2024-01-07 | 2024-01-28 | 21 | In Progress | 50% | Medium | 4200 | 0 | 743704 | — | —
32 | Trim Extra Spaces — Customer Name Import | Phase 4 | Rahul Mehta | Business Intel. | 2024-04-09 | 2024-04-21 | 12 | In Progress | 65% | Medium | 5500 | 80 | 397217 | Verified OK | Status, Priority
33 | Standardize Text Case — Region Codes | Phase 1 | Amit Roy | Data Platform | 2024-04-24 | 2024-05-22 | 28 | Completed | 0% | High | 4000 | 140 | 390182 | Verified OK | Name, Dept
34 | Fix Date Formats — Legacy System Dates | Phase 2 | Deepa Krishnan | Quality Assur. | 2024-03-06 | 2024-03-16 | 10 | Completed | 50% | Medium | 5000 | 60 | 526156 | Pending review | —
35 | Handle Missing Values — Customer Database | Phase 3 | Arjun Pillai | PMO | 2024-04-20 | 2024-04-30 | 10 | Completed | 50% | Critical | 2000 | 168 | 52880 | Pending review | Name, Dept
36 | Split Combined Columns — Contact Database | Phase 4 | Deepa Krishnan | BI & Analytics | 2024-04-01 | 2024-04-15 | 14 | In Progress | 50% | Medium | 4200 | 80 | 233464 | Verified OK | —
37 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Arjun Pillai | Business Intel. | 2024-05-29 | 2024-06-26 | 28 | Completed | 25% | High | 5500 | 120 | 320849 | Verified OK | Name, Phase
38 | Validate Data Ranges — HR Age Dataset | Phase 2 | Neha Joshi | Data Platform | 2024-05-19 | 2024-06-09 | 21 | Completed | 40% | High | 5000 | 0 | 769688 | — | Status, Priority
39 | Standardize Category Labels — Product SKU | Phase 3 | Karan Malhotra | Quality Assur. | 2024-05-19 | 2024-06-02 | 14 | In Progress | 75% | Low | 4000 | 0 | 130808 | Verified OK | Status, Priority
40 | Combine & Reconcile Columns — Address | Phase 4 | Pooja Iyer | PMO | 2024-05-07 | 2024-05-17 | 10 | In Progress | 75% | Medium | 3500 | 160 | 529775 | Verified OK | Name, Dept, Status
41 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Meera Pillai | BI & Analytics | 2024-02-28 | 2024-03-06 | 7 | Completed | 65% | Critical | 3000 | 60 | 473670 | Pending review | Status, Priority
42 | Trim Extra Spaces — Customer Name Import | Phase 2 | Rohit Gupta | Business Intel. | 2024-04-19 | 2024-04-29 | 10 | Not Started | 75% | Low | 5500 | 120 | 349673 | Verified OK | Status, Priority
43 | Standardize Text Case — Region Codes | Phase 3 | Ananya Singh | Data Platform | 2024-03-26 | 2024-04-09 | 14 | Not Started | 25% | Low | 4000 | 0 | 459027 | Check formula | Status, Priority
44 | Fix Date Formats — Legacy System Dates | Phase 4 | Rohit Gupta | Quality Assur. | 2024-01-10 | 2024-01-17 | 7 | Completed | 40% | Critical | 5500 | 0 | 297075 | — | —
45 | Handle Missing Values — Customer Database | Phase 1 | Lakshmi Nair | PMO | 2024-03-12 | 2024-03-26 | 14 | Not Started | 65% | Critical | 4000 | 60 | 172172 | Verified OK | Dept, Status
46 | Split Combined Columns — Contact Database | Phase 2 | Priya Sharma | BI & Analytics | 2024-01-27 | 2024-02-06 | 10 | Not Started | 100% | Medium | 3500 | 80 | 758761 | Verified OK | Phase, Priority
47 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Sunita Verma | Business Intel. | 2024-03-06 | 2024-03-13 | 7 | Completed | 40% | Medium | 4000 | 120 | 462749 | Needs validation | Name, Dept, Status
48 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | PMO | 2024-03-28 | 2024-04-04 | 7 | Not Started | 0% | Low | 5000 | 140 | 112639 | Verified OK | Dept, Status
49 | Standardize Category Labels — Product SKU | Phase 1 | Deepa Krishnan | Quality Assur. | 2024-01-08 | 2024-02-05 | 28 | Not Started | 75% | Low | 4000 | 120 | 871958 | — | Status, Priority
50 | Combine & Reconcile Columns — Address | Phase 2 | Vikram Nair | PMO | 2024-03-20 | 2024-03-27 | 7 | In Progress | 25% | Medium | 5000 | 0 | 288911 | Needs validation | Name, Dept, Status
51 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Arjun Pillai | BI & Analytics | 2024-01-27 | 2024-02-06 | 10 | Not Started | 0% | Critical | 4200 | 60 | 174169 | Needs validation | Dept, Status
52 | Trim Extra Spaces — Customer Name Import | Phase 4 | Arjun Pillai | Business Intel. | 2024-04-25 | 2024-05-07 | 12 | Not Started | 25% | High | 5000 | 100 | 841527 | — | Phase, Priority
53 | Standardize Text Case — Region Codes | Phase 1 | Neha Joshi | Data Platform | 2024-03-27 | 2024-04-17 | 21 | Not Started | 100% | High | 5000 | 168 | 448113 | — | Name, Dept, Status
54 | Fix Date Formats — Legacy System Dates | Phase 2 | Pooja Iyer | Quality Assur. | 2024-01-07 | 2024-01-17 | 10 | Completed | 65% | Critical | 3000 | 168 | 477451 | Pending review | Name, Dept
55 | Handle Missing Values — Customer Database | Phase 3 | Meera Pillai | PMO | 2024-02-09 | 2024-03-01 | 21 | Not Started | 65% | Medium | 4200 | 100 | 203594 | Needs validation | Dept, Status
56 | Split Combined Columns — Contact Database | Phase 4 | Ananya Singh | BI & Analytics | 2024-02-05 | 2024-02-12 | 7 | Not Started | 0% | Critical | 2000 | 168 | 844547 | Needs validation | Dept, Status
57 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Ananya Singh | Business Intel. | 2024-02-07 | 2024-02-28 | 21 | Completed | 100% | Low | 2000 | 168 | 509202 | — | Dept, Status
58 | Validate Data Ranges — HR Age Dataset | Phase 2 | Rohit Gupta | Data Platform | 2024-04-02 | 2024-04-30 | 28 | Not Started | 100% | Critical | 2000 | 120 | 353844 | — | —
59 | Standardize Category Labels — Product SKU | Phase 3 | Priya Sharma | Quality Assur. | 2024-01-25 | 2024-02-06 | 12 | In Progress | 50% | Critical | 5500 | 168 | 258384 | — | Name, Phase
60 | Combine & Reconcile Columns — Address | Phase 4 | Lakshmi Nair | PMO | 2024-01-08 | 2024-01-20 | 12 | In Progress | 75% | Medium | 3500 | 140 | 60120 | Needs validation | Name, Dept, Status
61 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Amit Roy | BI & Analytics | 2024-03-12 | 2024-03-24 | 12 | Completed | 75% | High | 2000 | 0 | 555848 | — | Name, Dept
62 | Trim Extra Spaces — Customer Name Import | Phase 2 | Sunita Verma | Business Intel. | 2024-03-28 | 2024-04-11 | 14 | Not Started | 75% | Critical | 4200 | 168 | 355120 | Extra spaces detected | Name, Dept, Status
63 | Standardize Text Case — Region Codes | Phase 3 | Vikram Nair | Data Platform | 2024-05-22 | 2024-06-19 | 28 | Completed | 0% | High | 4000 | 0 | 65625 | — | Name, Dept, Status
64 | Fix Date Formats — Legacy System Dates | Phase 4 | Vikram Nair | Quality Assur. | 2024-04-05 | 2024-04-26 | 21 | In Progress | 0% | Critical | 2000 | 120 | 431160 | Needs validation | Name, Dept
65 | Handle Missing Values — Customer Database | Phase 1 | Vikram Nair | PMO | 2024-04-10 | 2024-04-22 | 12 | In Progress | 75% | Medium | 4000 | 60 | 471106 | — | Dept, Status
66 | Split Combined Columns — Contact Database | Phase 2 | Deepa Krishnan | BI & Analytics | 2024-01-03 | 2024-01-24 | 21 | Completed | 0% | Critical | 5500 | 0 | 338896 | Extra spaces detected | Name, Phase
67 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Neha Joshi | Business Intel. | 2024-03-10 | 2024-03-20 | 10 | In Progress | 40% | High | 3000 | 160 | 400404 | — | Status, Priority
68 | Validate Data Ranges — HR Age Dataset | Phase 4 | Karan Malhotra | Data Platform | 2024-02-04 | 2024-02-18 | 14 | In Progress | 25% | Low | 2000 | 80 | 831470 | — | Status, Priority
69 | Standardize Category Labels — Product SKU | Phase 1 | Siddharth Rao | Quality Assur. | 2024-02-24 | 2024-03-16 | 21 | Not Started | 25% | High | 4000 | 80 | 718015 | Check formula | —
70 | Combine & Reconcile Columns — Address | Phase 2 | Pooja Iyer | PMO | 2024-03-30 | 2024-04-09 | 10 | Not Started | 50% | High | 2000 | 60 | 719345 | — | Phase, Priority
71 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Meera Pillai | BI & Analytics | 2024-05-12 | 2024-05-26 | 14 | In Progress | 0% | Critical | 4200 | 140 | 197919 | — | Name, Phase
72 | Trim Extra Spaces — Customer Name Import | Phase 4 | Meera Pillai | Business Intel. | 2024-01-16 | 2024-01-23 | 7 | Not Started | 50% | High | 2000 | 160 | 351364 | Pending review | Name, Dept, Status
73 | Standardize Text Case — Region Codes | Phase 1 | Rohit Gupta | Data Platform | 2024-01-03 | 2024-01-24 | 21 | Not Started | 25% | High | 2000 | 80 | 532507 | Verified OK | —
74 | Fix Date Formats — Legacy System Dates | Phase 2 | Rohit Gupta | Quality Assur. | 2024-03-06 | 2024-03-18 | 12 | In Progress | 40% | Low | 3500 | 80 | 718869 | — | Dept, Status
75 | Handle Missing Values — Customer Database | Phase 3 | Rahul Mehta | PMO | 2024-01-30 | 2024-02-09 | 10 | Completed | 0% | Medium | 2000 | 60 | 364736 | — | Dept, Status
76 | Split Combined Columns — Contact Database | Phase 4 | Priya Sharma | BI & Analytics | 2024-05-19 | 2024-06-02 | 14 | Completed | 40% | High | 5000 | 0 | 564589 | — | Name, Phase
77 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Rahul Mehta | Business Intel. | 2024-05-14 | 2024-05-21 | 7 | Not Started | 25% | High | 3000 | 100 | 611199 | — | —
78 | Validate Data Ranges — HR Age Dataset | Phase 2 | Vikram Nair | Data Platform | 2024-02-24 | 2024-03-16 | 21 | Completed | 100% | High | 3500 | 120 | 213375 | Verified OK | —
79 | Standardize Category Labels — Product SKU | Phase 3 | Vikram Nair | Quality Assur. | 2024-01-14 | 2024-01-28 | 14 | Completed | 40% | Low | 3500 | 100 | 137482 | Extra spaces detected | Phase, Priority
80 | Combine & Reconcile Columns — Address | Phase 4 | Arjun Pillai | PMO | 2024-01-09 | 2024-02-06 | 28 | In Progress | 100% | Low | 3000 | 160 | 106825 | Verified OK | Name, Phase
81 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Neha Joshi | BI & Analytics | 2024-01-15 | 2024-01-22 | 7 | Not Started | 0% | Critical | 3000 | 160 | 74549 | — | Phase, Priority
82 | Trim Extra Spaces — Customer Name Import | Phase 2 | Neha Joshi | Business Intel. | 2024-02-11 | 2024-02-25 | 14 | Not Started | 75% | Medium | 5000 | 100 | 138639 | Needs validation | Name, Dept, Status
83 | Standardize Text Case — Region Codes | Phase 3 | Karan Malhotra | Data Platform | 2024-01-18 | 2024-01-30 | 12 | In Progress | 75% | High | 2000 | 0 | 429191 | Pending review | Status, Priority
84 | Fix Date Formats — Legacy System Dates | Phase 4 | Pooja Iyer | Quality Assur. | 2024-01-17 | 2024-01-31 | 14 | Completed | 40% | Low | 4200 | 140 | 410872 | Check formula | —
85 | Handle Missing Values — Customer Database | Phase 1 | Siddharth Rao | PMO | 2024-04-12 | 2024-04-26 | 14 | Not Started | 75% | Low | 5000 | 100 | 488003 | — | —
86 | Split Combined Columns — Contact Database | Phase 2 | Meera Pillai | BI & Analytics | 2024-02-02 | 2024-02-23 | 21 | In Progress | 25% | Medium | 3500 | 0 | 213101 | — | —
87 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Rohit Gupta | Business Intel. | 2024-03-22 | 2024-04-12 | 21 | Not Started | 0% | Critical | 5500 | 140 | 578168 | — | Status, Priority
88 | Validate Data Ranges — HR Age Dataset | Phase 4 | Lakshmi Nair | Data Platform | 2024-03-04 | 2024-03-18 | 14 | Not Started | 50% | Critical | 3000 | 60 | 217697 | Check formula | Name, Dept
89 | Standardize Category Labels — Product SKU | Phase 1 | Lakshmi Nair | Quality Assur. | 2024-02-28 | 2024-03-13 | 14 | In Progress | 40% | Low | 3000 | 160 | 652750 | Check formula | Dept, Status
90 | Combine & Reconcile Columns — Address | Phase 2 | Rahul Mehta | PMO | 2024-04-25 | 2024-05-09 | 14 | Completed | 0% | Medium | 4200 | 0 | 605806 | Needs validation | Phase, Priority
91 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Rahul Mehta | BI & Analytics | 2024-05-10 | 2024-05-22 | 12 | Completed | 75% | Low | 4000 | 80 | 88135 | Extra spaces detected | Phase, Priority
92 | Trim Extra Spaces — Customer Name Import | Phase 4 | Amit Roy | Business Intel. | 2024-02-23 | 2024-03-22 | 28 | Completed | 100% | Low | 2000 | 120 | 180191 | — | Name, Phase
93 | Standardize Text Case — Region Codes | Phase 1 | Sunita Verma | Data Platform | 2024-02-11 | 2024-02-18 | 7 | In Progress | 50% | Critical | 2000 | 100 | 735602 | Needs validation | Name, Dept, Status
94 | Fix Date Formats — Legacy System Dates | Phase 2 | Vikram Nair | Quality Assur. | 2024-02-01 | 2024-02-13 | 12 | In Progress | 65% | Low | 3000 | 160 | 793885 | Verified OK | Name, Dept
95 | Handle Missing Values — Customer Database | Phase 3 | Deepa Krishnan | PMO | 2024-05-05 | 2024-05-12 | 7 | In Progress | 0% | Low | 5500 | 140 | 561639 | Needs validation | —
96 | Split Combined Columns — Contact Database | Phase 4 | Neha Joshi | BI & Analytics | 2024-01-28 | 2024-02-25 | 28 | In Progress | 25% | Critical | 2000 | 80 | 247793 | — | Name, Dept, Status
97 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Karan Malhotra | Business Intel. | 2024-05-05 | 2024-05-19 | 14 | Not Started | 50% | Medium | 4000 | 168 | 131140 | Needs validation | Dept, Status
98 | Validate Data Ranges — HR Age Dataset | Phase 2 | Karan Malhotra | Data Platform | 2024-05-30 | 2024-06-09 | 10 | In Progress | 40% | High | 3000 | 80 | 171017 | Check formula | —
99 | Standardize Category Labels — Product SKU | Phase 3 | Pooja Iyer | Quality Assur. | 2024-01-30 | 2024-02-11 | 12 | In Progress | 25% | Low | 4200 | 168 | 769059 | Check formula | —
100 | Combine & Reconcile Columns — Address | Phase 4 | Meera Pillai | PMO | 2024-03-16 | 2024-04-06 | 21 | In Progress | 65% | Critical | 3500 | 60 | 719820 | Needs validation | Name, Dept
101 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Siddharth Rao | BI & Analytics | 2024-02-17 | 2024-03-09 | 21 | In Progress | 25% | High | 5000 | 100 | 109309 | Check formula | Name, Dept
102 | Trim Extra Spaces — Customer Name Import | Phase 2 | Rohit Gupta | Business Intel. | 2024-01-01 | 2024-01-29 | 28 | Not Started | 40% | Medium | 5500 | 168 | 385927 | Needs validation | Status, Priority
103 | Standardize Text Case — Region Codes | Phase 3 | Lakshmi Nair | Data Platform | 2024-01-07 | 2024-01-17 | 10 | Completed | 50% | Critical | 3500 | 120 | 701196 | Check formula | Name, Dept, Status
104 | Fix Date Formats — Legacy System Dates | Phase 4 | Rohit Gupta | Quality Assur. | 2024-01-05 | 2024-01-26 | 21 | Completed | 25% | High | 4200 | 60 | 295747 | Check formula | Name, Dept, Status
105 | Handle Missing Values — Customer Database | Phase 1 | Priya Sharma | PMO | 2024-02-19 | 2024-03-11 | 21 | In Progress | 75% | Medium | 5000 | 80 | 859197 | — | Name, Phase
106 | Split Combined Columns — Contact Database | Phase 2 | Amit Roy | BI & Analytics | 2024-01-19 | 2024-01-26 | 7 | In Progress | 0% | Low | 3500 | 120 | 889984 | Verified OK | Dept, Status
107 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Amit Roy | Business Intel. | 2024-04-19 | 2024-05-17 | 28 | Not Started | 0% | Low | 5000 | 60 | 730288 | — | Name, Dept, Status
108 | Validate Data Ranges — HR Age Dataset | Phase 4 | Sunita Verma | Data Platform | 2024-01-07 | 2024-01-21 | 14 | Completed | 100% | Critical | 2000 | 100 | 524996 | — | Status, Priority
109 | Standardize Category Labels — Product SKU | Phase 1 | Sunita Verma | Quality Assur. | 2024-05-02 | 2024-05-09 | 7 | Completed | 40% | Critical | 3000 | 140 | 424476 | — | Dept, Status
110 | Combine & Reconcile Columns — Address | Phase 2 | Arjun Pillai | PMO | 2024-01-09 | 2024-01-16 | 7 | Completed | 100% | High | 2000 | 160 | 696213 | Verified OK | Name, Dept, Status
111 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Deepa Krishnan | BI & Analytics | 2024-05-09 | 2024-05-30 | 21 | Completed | 0% | Critical | 3000 | 60 | 218588 | — | —
112 | Trim Extra Spaces — Customer Name Import | Phase 4 | Neha Joshi | Business Intel. | 2024-03-10 | 2024-03-24 | 14 | In Progress | 100% | Critical | 5500 | 80 | 72144 | Pending review | Status, Priority
113 | Standardize Text Case — Region Codes | Phase 1 | Neha Joshi | Data Platform | 2024-05-08 | 2024-06-05 | 28 | Completed | 75% | Low | 5000 | 140 | 326672 | Verified OK | Phase, Priority
114 | Fix Date Formats — Legacy System Dates | Phase 2 | Siddharth Rao | Quality Assur. | 2024-04-26 | 2024-05-10 | 14 | In Progress | 65% | Medium | 4000 | 60 | 321071 | — | Name, Dept
115 | Handle Missing Values — Customer Database | Phase 3 | Pooja Iyer | PMO | 2024-05-29 | 2024-06-08 | 10 | In Progress | 40% | Medium | 4200 | 80 | 419491 | Verified OK | —
116 | Split Combined Columns — Contact Database | Phase 4 | Ananya Singh | BI & Analytics | 2024-03-11 | 2024-03-23 | 12 | In Progress | 100% | High | 4000 | 80 | 399625 | Check formula | Dept, Status
117 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Rohit Gupta | Business Intel. | 2024-04-21 | 2024-05-03 | 12 | Not Started | 50% | Critical | 4200 | 140 | 63596 | — | —
118 | Validate Data Ranges — HR Age Dataset | Phase 2 | Lakshmi Nair | Data Platform | 2024-04-12 | 2024-04-26 | 14 | Completed | 40% | Critical | 5000 | 80 | 326568 | Needs validation | Name, Phase
119 | Standardize Category Labels — Product SKU | Phase 3 | Lakshmi Nair | Quality Assur. | 2024-03-13 | 2024-03-25 | 12 | Completed | 0% | Critical | 4200 | 80 | 160535 | Verified OK | Status, Priority
120 | Combine & Reconcile Columns — Address | Phase 4 | Lakshmi Nair | PMO | 2024-04-04 | 2024-04-16 | 12 | In Progress | 50% | High | 4200 | 80 | 168671 | Needs validation | Name, Phase
121 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Rahul Mehta | BI & Analytics | 2024-03-25 | 2024-04-22 | 28 | Not Started | 0% | Low | 5500 | 60 | 825744 | Check formula | —
122 | Trim Extra Spaces — Customer Name Import | Phase 2 | Sunita Verma | Business Intel. | 2024-01-17 | 2024-02-07 | 21 | Not Started | 40% | Medium | 3500 | 140 | 65426 | — | Name, Dept, Status
123 | Standardize Text Case — Region Codes | Phase 3 | Amit Roy | Data Platform | 2024-02-13 | 2024-02-20 | 7 | Not Started | 75% | Low | 3000 | 0 | 764971 | — | Name, Dept
124 | Fix Date Formats — Legacy System Dates | Phase 4 | Deepa Krishnan | Quality Assur. | 2024-05-21 | 2024-06-02 | 12 | Completed | 25% | Medium | 5000 | 0 | 59442 | — | —
125 | Handle Missing Values — Customer Database | Phase 1 | Deepa Krishnan | PMO | 2024-05-12 | 2024-06-02 | 21 | In Progress | 50% | Low | 2000 | 100 | 754802 | Needs validation | Name, Phase
126 | Split Combined Columns — Contact Database | Phase 2 | Deepa Krishnan | BI & Analytics | 2024-02-23 | 2024-03-08 | 14 | Completed | 25% | Critical | 3000 | 168 | 832007 | Extra spaces detected | Status, Priority
127 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Arjun Pillai | Business Intel. | 2024-01-28 | 2024-02-09 | 12 | In Progress | 75% | Medium | 5000 | 160 | 558708 | — | Name, Phase
128 | Validate Data Ranges — HR Age Dataset | Phase 4 | Karan Malhotra | Data Platform | 2024-05-08 | 2024-05-22 | 14 | In Progress | 50% | Medium | 4200 | 168 | 242071 | Extra spaces detected | —
129 | Standardize Category Labels — Product SKU | Phase 1 | Siddharth Rao | Quality Assur. | 2024-01-09 | 2024-01-21 | 12 | In Progress | 65% | Medium | 4000 | 100 | 44899 | — | Status, Priority
130 | Combine & Reconcile Columns — Address | Phase 2 | Pooja Iyer | PMO | 2024-03-23 | 2024-04-06 | 14 | In Progress | 0% | High | 2000 | 0 | 219184 | — | Name, Dept
131 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Meera Pillai | BI & Analytics | 2024-04-06 | 2024-04-18 | 12 | Not Started | 0% | High | 5500 | 0 | 281886 | Check formula | Name, Dept
132 | Trim Extra Spaces — Customer Name Import | Phase 4 | Rohit Gupta | Business Intel. | 2024-02-29 | 2024-03-14 | 14 | Not Started | 0% | Medium | 4200 | 140 | 647486 | Check formula | —
133 | Standardize Text Case — Region Codes | Phase 1 | Lakshmi Nair | Data Platform | 2024-03-30 | 2024-04-13 | 14 | In Progress | 65% | High | 5500 | 100 | 612608 | Pending review | Dept, Status
134 | Fix Date Formats — Legacy System Dates | Phase 2 | Priya Sharma | Quality Assur. | 2024-04-07 | 2024-05-05 | 28 | Not Started | 75% | Medium | 2000 | 140 | 487550 | Pending review | Name, Dept, Status
135 | Handle Missing Values — Customer Database | Phase 3 | Rahul Mehta | PMO | 2024-01-28 | 2024-02-09 | 12 | Completed | 0% | Critical | 3000 | 120 | 499193 | — | Name, Phase
136 | Split Combined Columns — Contact Database | Phase 4 | Priya Sharma | BI & Analytics | 2024-05-14 | 2024-06-11 | 28 | Not Started | 0% | Critical | 2000 | 80 | 299234 | Verified OK | Dept, Status
137 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Amit Roy | Business Intel. | 2024-04-28 | 2024-05-05 | 7 | Not Started | 75% | High | 4200 | 140 | 866835 | Check formula | Dept, Status
138 | Validate Data Ranges — HR Age Dataset | Phase 2 | Amit Roy | Data Platform | 2024-03-20 | 2024-04-01 | 12 | In Progress | 25% | High | 5000 | 168 | 268864 | Verified OK | Name, Dept
139 | Standardize Category Labels — Product SKU | Phase 3 | Deepa Krishnan | Quality Assur. | 2024-04-24 | 2024-05-01 | 7 | Not Started | 100% | Critical | 2000 | 120 | 241734 | — | —
140 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | PMO | 2024-04-28 | 2024-05-10 | 12 | In Progress | 0% | Critical | 5500 | 160 | 625386 | Needs validation | Status, Priority
141 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Neha Joshi | BI & Analytics | 2024-02-25 | 2024-03-03 | 7 | In Progress | 75% | Critical | 3500 | 60 | 576816 | Check formula | Name, Dept, Status
142 | Trim Extra Spaces — Customer Name Import | Phase 2 | Arjun Pillai | Business Intel. | 2024-04-28 | 2024-05-10 | 12 | In Progress | 100% | Medium | 3000 | 0 | 813795 | Check formula | Name, Dept, Status
143 | Standardize Text Case — Region Codes | Phase 3 | Karan Malhotra | Data Platform | 2024-01-31 | 2024-02-12 | 12 | Completed | 100% | Low | 3500 | 160 | 340685 | — | Phase, Priority
144 | Fix Date Formats — Legacy System Dates | Phase 4 | Siddharth Rao | Quality Assur. | 2024-04-09 | 2024-04-16 | 7 | In Progress | 25% | Medium | 2000 | 160 | 362796 | Extra spaces detected | Name, Dept
145 | Handle Missing Values — Customer Database | Phase 1 | Siddharth Rao | PMO | 2024-01-31 | 2024-02-28 | 28 | In Progress | 0% | Critical | 3500 | 60 | 153755 | — | Dept, Status
146 | Split Combined Columns — Contact Database | Phase 2 | Ananya Singh | BI & Analytics | 2024-05-06 | 2024-05-18 | 12 | Not Started | 50% | Critical | 5500 | 80 | 570184 | — | —
147 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Meera Pillai | Business Intel. | 2024-05-05 | 2024-06-02 | 28 | Completed | 50% | Critical | 5000 | 140 | 46584 | Pending review | Phase, Priority
148 | Validate Data Ranges — HR Age Dataset | Phase 4 | Ananya Singh | Data Platform | 2024-02-11 | 2024-02-21 | 10 | Not Started | 65% | Critical | 3000 | 168 | 640222 | Check formula | Dept, Status
149 | Standardize Category Labels — Product SKU | Phase 1 | Rohit Gupta | Quality Assur. | 2024-02-21 | 2024-03-04 | 12 | In Progress | 75% | High | 5000 | 120 | 198826 | Verified OK | Name, Dept
150 | Combine & Reconcile Columns — Address | Phase 2 | Lakshmi Nair | PMO | 2024-05-05 | 2024-05-12 | 7 | Not Started | 40% | Medium | 3000 | 0 | 340075 | — | Dept, Status

## Gantt Chart
📅 GANTT CHART — Data Cleaning for Excel Dashboard Development ¦ January 2024 – June 2024 ¦ 4 Phases ¦ 10 Techniques
← Back to Project Overview ¦ Jan – Jun 2024 ¦ 4 Phases ¦ 10 Techniques
# | Task / Technique | Phase | Owner | Start | End | Days | Status | % Done | Priority | January 2024 |  |  |  | February 2024 |  |  |  | March 2024 |  |  |  | April 2024 |  |  |  | May 2024 |  |  |  | June 2024
[10 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PHASE 1 — Foundation Cleaning (Techniques 1–3)
1 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Priya Sharma | 2024-01-01 | 2024-01-15 | 14 | Completed | 100% | Critical
2 | Trim Extra Spaces — Customer Name Import | Phase 1 | Rahul Mehta | 2024-01-08 | 2024-01-18 | 10 | Completed | 100% | Critical
3 | Standardize Text Case — Region Codes | Phase 1 | Neha Joshi | 45306 | 45316 | 10 | Completed | 1 | High
PHASE 2 — Structure & Format Cleaning (Techniques 4–6)
4 | Fix Date Formats — Legacy System Dates | Phase 2 | Amit Roy | 2024-01-29 | 2024-02-12 | 14 | Completed | 100% | Critical
5 | Handle Missing Values — Customer Database | Phase 2 | Sunita Verma | 2024-02-05 | 2024-02-19 | 14 | Completed | 100% | High
6 | Split Combined Columns — Contact Database | Phase 2 | Karan Malhotra | 45334 | 45346 | 12 | In Progress | 0.65 | Medium
PHASE 3 — Value Validation & Standardisation (Techniques 7–9)
7 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Amit Roy | 2024-03-04 | 2024-03-18 | 14 | In Progress | 40% | Critical
8 | Validate Data Ranges — HR Age Dataset | Phase 3 | Pooja Iyer | 2024-03-11 | 2024-03-25 | 14 | Not Started | 0% | High
9 | Standardize Category Labels — Product SKU | Phase 3 | Siddharth Rao | 45369 | 45383 | 14 | Not Started | 0 | High
PHASE 4 — Data Consolidation & Final QA (Technique 10)
10 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | 2024-04-15 | 2024-04-29 | 14 | Not Started | 0% | Medium
LEGEND | Phase 1 – Foundation | Phase 2 – Structure | Phase 3 – Validation | Phase 4 – Final QA | ■ Completed | ■ In Progress | ■ Not Started

## Resource Planner
👥 RESOURCE ALLOCATION PLANNER — Data Cleaning Project ¦ Team capacity, task assignments, workload & availability — Jan to Jun 2024
← Back to Project Overview
# | Resource Name | Role | Department | Techniques Assigned | Ph.1 | Ph.2 | Ph.3 | Ph.4 | Total Tasks | Daily Rate (₹) | Hours Alloc. | Availability % | Utilisation % | Status
1 | Priya Sharma | Senior Data Analyst | BI & Analytics | COUNTIF, TRIM, CLEAN, VLOOKUP, ISBLANK | 2 | 2 | 1 | 0 | 5 | 3500 | 168 | 90% | 85% | Active
2 | Rahul Mehta | BI Developer | Business Intel. | UPPER/LOWER/PROPER, TEXTSPLIT, LEFT/MID | 1 | 1 | 1 | 0 | 3 | 4000 | 140 | 80% | 78% | Active
3 | Amit Roy | Data Engineer | Data Platform | DATEVALUE, VALUE, DATE, TEXTJOIN | 0 | 1 | 1 | 1 | 3 | 4200 | 160 | 95% | 90% | Active
4 | Sunita Verma | QA Analyst | Quality Assur. | IFERROR, ISBLANK, AVERAGEIFS, IF, AND | 0 | 1 | 1 | 1 | 3 | 3000 | 120 | 70% | 65% | Active
5 | Karan Malhotra | Project Manager | PMO | Project Planning, Reporting, Stakeholder | 1 | 1 | 1 | 1 | 4 | 5000 | 80 | 60% | 55% | Active
6 | Deepa Krishnan | Junior Data Analyst | BI & Analytics | TRIM, CLEAN, VLOOKUP, COUNTIF | 1 | 1 | 0 | 0 | 2 | 2000 | 80 | 100% | 70% | Active
7 | Neha Joshi | Data Architect | Data Platform | Data Modelling, ETL, Schema, Validation | 0 | 0 | 1 | 1 | 2 | 5500 | 60 | 50% | 45% | Part-time
TOTALS / AVERAGES |  |  |  |  | 5 | 7 | 6 | 4 | 22 | 3885.7143 | 808 | 77.86% | 69.71%
WORKLOAD SUMMARY BY PHASE
Resource | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total Tasks | Hours | Util %
Priya Sharma | 2 | 2 | 1 | 0 | 5 | 168 | 85%
Rahul Mehta | 1 | 1 | 1 | 0 | 3 | 140 | 78%
Amit Roy | 0 | 1 | 1 | 1 | 3 | 160 | 90%
Sunita Verma | 0 | 1 | 1 | 1 | 3 | 120 | 65%
Karan Malhotra | 1 | 1 | 1 | 1 | 4 | 80 | 55%
Deepa Krishnan | 1 | 1 | 0 | 0 | 2 | 80 | 70%
Neha Joshi | 0 | 0 | 1 | 1 | 2 | 60 | 45%

## Task Tracker
✅ TASK TRACKER — Data Cleaning for Excel Dashboard ¦ Detailed task log with formulas, dependencies, review dates & completion tracking
← Back to Project Overview
# | Technique / Task | Phase | Owner | Priority | Start Date | End Date | Duration | Status | % Complete | Notes / Formula Used | Dependency | Review Date | ▶ Live Formula (click me!) | Sample Data (reference)
1 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Priya Sharma | Critical | 2024-01-01 | 2024-01-15 | 14 | Completed | 100% | COUNTIF($A$2:$A2,A2)>1 ¦ Data > Remove Duplicates | None | 2024-01-17 | FALSE | ORD-1001
2 | Trim Extra Spaces — Customer Name Import | Phase 1 | Rahul Mehta | Critical | 2024-01-08 | 2024-01-18 | 10 | Completed | 100% | TRIM(CLEAN(A2)) | Task 1 | 2024-01-20 | Priya Sharma | Priya Sharma
3 | Standardize Text Case — Region Codes | Phase 1 | Neha Joshi | High | 2024-01-15 | 2024-01-25 | 10 | Completed | 100% | PROPER(A2) ¦ UPPER(A2) ¦ LOWER(A2) | Task 2 | 2024-01-27 | North West | north west
4 | Fix Date Formats — Legacy System Dates | Phase 2 | Amit Roy | Critical | 2024-01-29 | 2024-02-12 | 14 | Completed | 100% | DATEVALUE(A2) ¦ DATE(RIGHT,MID,LEFT) | Task 3 | 2024-02-14 | 45320 | 2024-01-29
5 | Handle Missing Values — Customer Database | Phase 2 | Sunita Verma | High | 2024-02-05 | 2024-02-19 | 14 | Completed | 100% | IF(ISBLANK(A2),"Unknown",A2) | Task 4 | 2024-02-21 | Unknown
6 | Split Combined Columns — Contact Database | Phase 2 | Karan Malhotra | Medium | 2024-02-12 | 2024-02-24 | 12 | In Progress | 65% | LEFT(A2,FIND(" ",A2)-1) ¦ MID(A2,FIND(...)) | Task 5 | 2024-02-26 | Karan | Karan Malhotra
7 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Amit Roy | Critical | 2024-03-04 | 2024-03-18 | 14 | In Progress | 40% | VALUE(SUBSTITUTE(SUBSTITUTE(A2,"Rs. ",""),",","")) | Task 6 | 2024-03-20 | 150000 | Rs. 1,50,000
8 | Validate Data Ranges — HR Age Dataset | Phase 3 | Pooja Iyer | High | 2024-03-11 | 2024-03-25 | 14 | Not Started | 0% | IF(AND(A2>=18,A2<=65),"Valid","Invalid") | Task 7 | 2024-03-27 | Valid | 45
9 | Standardize Category Labels — Product SKU | Phase 3 | Siddharth Rao | High | 2024-03-18 | 2024-04-01 | 14 | Not Started | 0% | IFERROR(VLOOKUP(UPPER(A2),MapTable,2,0),PROPER(A2)) | Task 8 | 2024-04-03 | Electronics | electronics
10 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | Medium | 2024-04-15 | 2024-04-29 | 14 | Not Started | 0% | TEXTJOIN(", ",TRUE,B2,C2,D2) | Task 9 | 2024-05-01 | 123 Main St, Mumbai, 400001 | 123 Main St

## Data Reference
📖 DATA CLEANING REFERENCE — Raw vs Clean Data Examples ¦ All 10 techniques with before/after data
← Back to Project Overview
Technique 1 — Remove Duplicates
← RAW DATA (Before Cleaning)
Order ID | Customer | Product | Amount (₹) | Date
ORD-1001 | Priya Sharma | Laptop | ₹75,000 | 01-Jan-2024
ORD-1002 | Rahul Mehta | Wireless Mouse | ₹1,200 | 02-Jan-2024
ORD-1001 | Priya Sharma | Laptop | ₹75,000 | 01-Jan-2024 ← DUP
ORD-1003 | Deepa Krishnan | Keyboard | ₹2,500 | 03-Jan-2024
ORD-1002 | Rahul Mehta | Wireless Mouse | ₹1,200 | 02-Jan-2024 ← DUP
✔ CLEAN DATA (After Cleaning)
Order ID | Customer | Product | Amount (₹) | Date
ORD-1001 | Priya Sharma | Laptop | ₹75,000 | 01-Jan-2024
ORD-1002 | Rahul Mehta | Wireless Mouse | ₹1,200 | 02-Jan-2024
ORD-1003 | Deepa Krishnan | Keyboard | ₹2,500 | 03-Jan-2024
Technique 2 — Trim Extra Spaces
← RAW DATA (Before Cleaning)
Cust ID | Raw Name (Spaces) | Email
C001 | Priya Sharma | priya@corp.in
C002 | Rahul Mehta | rahul@corp.in
C003 | Neha Joshi | neha@corp.in
C004 | Sunita Verma | sunita@corp.in
✔ CLEAN DATA (After Cleaning)
Cust ID | Raw Name (Spaces) | Email
C001 | Priya Sharma | priya@corp.in
C002 | Rahul Mehta | rahul@corp.in
C003 | Neha Joshi | neha@corp.in
C004 | Sunita Verma | sunita@corp.in
Technique 3 — Standardize Text Case
← RAW DATA (Before Cleaning)
Sales Rep | Region (Raw) | Revenue (₹)
Rep A | north | ₹1,20,000
Rep B | SOUTH | ₹98,000
Rep C | North | ₹2,10,000
Rep D | south | ₹75,000
Rep E | NORTH | ₹1,50,000
✔ CLEAN DATA (After Cleaning)
Sales Rep | Region (Raw) | Revenue (₹)
Rep A | North | ₹1,20,000
Rep B | South | ₹98,000
Rep C | North | ₹2,10,000
Rep D | South | ₹75,000
Rep E | North | ₹1,50,000
Technique 4 — Fix Date Formats
← RAW DATA (Before Cleaning)
Emp ID | Date (Raw Text) | Dept
E001 | 01-01-2024 | HR
E002 | 2024/01/15 | Finance
E003 | Jan 20 2024 | Sales
E004 | 20240125 | IT
✔ CLEAN DATA (After Cleaning)
Emp ID | Date (Raw Text) | Dept
E001 | 01-Jan-2024 | HR
E002 | 15-Jan-2024 | Finance
E003 | 20-Jan-2024 | Sales
E004 | 25-Jan-2024 | IT
Technique 5 — Handle Missing Values
← RAW DATA (Before Cleaning)
Cust ID | Name | Region | Score
C001 | Priya Sharma | North | 85
C002 |  | South
C003 | Karan Malhotra |  | 72
C004 | Sunita Verma | East
✔ CLEAN DATA (After Cleaning)
Cust ID | Name | Region | Score
C001 | Priya Sharma | North | 85
C002 | Unknown | South | 0
C003 | Karan Malhotra | Unassigned | 72
C004 | Sunita Verma | East | 0
Technique 6 — Split Combined Columns
← RAW DATA (Before Cleaning)
Full Name | First Name | Last Name | Email
Priya Sharma |  |  | priya@corp.in
Rahul Mehta |  |  | rahul@corp.in
Deepa Krishnan |  |  | deepa@corp.in
✔ CLEAN DATA (After Cleaning)
Full Name | First Name | Last Name | Email
Priya Sharma | Priya | Sharma | priya@corp.in
Rahul Mehta | Rahul | Mehta | rahul@corp.in
Deepa Krishnan | Deepa | Krishnan | deepa@corp.in
Technique 7 — Remove Non-Numeric Chars
← RAW DATA (Before Cleaning)
Product | Revenue (Raw) | Units
Laptop | Rs. 7,50,000 | 10
Mouse | Rs. 12,000 | 100
Monitor | ₹3,20,000 | 32
Keyboard | INR 45,000 | 50
✔ CLEAN DATA (After Cleaning)
Product | Revenue (Raw) | Units
Laptop | 750000 | 10
Mouse | 12000 | 100
Monitor | 320000 | 32
Keyboard | 45000 | 50
Technique 8 — Validate Data Ranges
← RAW DATA (Before Cleaning)
Emp ID | Age | Dept | Valid?
E001 | 25 | HR
E002 | 17 | Finance
E003 | 45 | Sales
E004 | 72 | IT
✔ CLEAN DATA (After Cleaning)
Emp ID | Age | Dept | Valid?
E001 | 25 | HR | Valid
E002 | 17 | Finance | Invalid
E003 | 45 | Sales | Valid
E004 | 72 | IT | Invalid
Technique 9 — Standardize Category Labels
← RAW DATA (Before Cleaning)
SKU | Category (Raw) | Std Category
SKU-01 | laptop
SKU-02 | LAPTOP
SKU-03 | Lap Top
SKU-04 | Mouse
✔ CLEAN DATA (After Cleaning)
SKU | Category (Raw) | Std Category
SKU-01 | laptop | Laptop
SKU-02 | LAPTOP | Laptop
SKU-03 | Lap Top | Laptop
SKU-04 | Mouse | Mouse
Technique 10 — Combine & Reconcile Columns
← RAW DATA (Before Cleaning)
First | Last | City | Pincode | Full Address
Priya | Sharma | Mumbai | 400001
Rahul | Mehta | Delhi | 110001
Deepa | Krishnan | Bangalore | 560001
✔ CLEAN DATA (After Cleaning)
First | Last | City | Pincode | Full Address
Priya | Sharma | Mumbai | 400001 | Priya Sharma, Mumbai, 400001
Rahul | Mehta | Delhi | 110001 | Rahul Mehta, Delhi, 110001
Deepa | Krishnan | Bangalore | 560001 | Deepa Krishnan, Bangalore, 560001

## Formula Cheat Sheet
🔢 FORMULA CHEAT SHEET — Data Cleaning for Excel Dashboard ¦ Quick reference: all key formulas with syntax, notes and technique mapping
← Back to Project Overview
# | Task | Formula / Syntax | Notes | Technique | Sample Input | ▶ Live Formula (click me!)
1 | Find duplicates | COUNTIF($A$2:$A2, A2) > 1 | TRUE = duplicate row; filter & delete | T1 | ORD-1001 | FALSE
2 | Remove duplicates (UI) | Data > Remove Duplicates > Select columns > OK | Select key column (e.g. Order ID) | T1 | (UI action) | Use: Data → Remove Duplicates
3 | Remove extra spaces | TRIM(CLEAN(A2)) | Handles spaces + invisible chars (ASCII 0-31) | T2 | Priya Sharma | Priya Sharma
4 | Title case | PROPER(A2) | First letter of each word capitalised | T3 | north west region | North West Region
5 | Upper case | UPPER(A2) | Use for codes, IDs, email addresses | T3 | invoice ref | INVOICE REF
6 | Lower case | LOWER(A2) | Use for email standardisation | T3 | PRIYA.SHARMA@CORP | priya.sharma@corp
7 | Convert date text | DATEVALUE(A2) | Format result cell as Date after applying | T4 | 2024-01-15 | 45306
8 | Build date from parts | DATE(RIGHT(A2,4), MID(A2,4,2), LEFT(A2,2)) | For DD-MM-YYYY text format | T4 | 15-01-2024 | 2024-01-15
9 | Fill blank text | IF(ISBLANK(A2), "Unknown", A2) | Replace blank with a default label | T5 |  | Unknown
10 | Fill blank number | IF(ISBLANK(A2), 0, A2) | Replace blank numeric cell with zero | T5 |  | 0
11 | Trap formula errors | IFERROR(your_formula, "N/A") | Wrap any formula to catch all errors | T5 | N/A | N/A
12 | First name | LEFT(A2, FIND(" ", A2)-1) | Extracts text before the first space | T6 | Priya Sharma | Priya
13 | Last name | MID(A2, FIND(" ", A2)+1, LEN(A2)) | Extracts text after the first space | T6 | Priya Sharma | Sharma
14 | Remove "Rs." & commas | VALUE(SUBSTITUTE(SUBSTITUTE(A2,"Rs. ",""),",","")) | Convert to number; format as Currency | T7 | Rs. 1,50,000 | 150000
15 | Flag out-of-range | IF(AND(A2>=18, A2<=65), "Valid", "Invalid") | Adjust min/max bounds as required | T8 | 45 | Valid
16 | Avg ignoring outliers | AVERAGEIFS(A2:A10, A2:A10, ">="&18, A2:A10, "<="&65) | Only averages values in valid range | T8 | 42 | 43.5
17 | Count valid range | COUNTIFS(A2:A10, ">="&18, A2:A10, "<="&65) | Count numeric rows within valid bounds | T8 | 28 | 2
18 | Standardise via lookup | IFERROR(VLOOKUP(UPPER(A2), MapTable, 2, 0), PROPER(A2)) | Needs 2-col mapping table | T9 | Electronics | (Needs MapTable) ELECTRONICS
19 | Join columns | TEXTJOIN(", ", TRUE, A2, B2, C2) | Skips blanks automatically (TRUE) | T10 | 123 Main St | 123 Main St, Mumbai, 400001
20 | Composite unique key | A2 & "-" & TEXT(B2, "YYYYMMDD") | Creates e.g. C001-20240115 | T10 | C001 | C001-20260519

## Dashboard Checklist
📋 DASHBOARD READINESS CHECKLIST — Pre-Deployment Quality Gate ¦ Verify all 10 items before connecting cleaned dataset to the Excel Dashboard
← Back to Project Overview
# | Checklist Item | How to Verify | Responsible | Due Date | Status
1 | No duplicate rows | COUNTIF on key column — all values = 1 | Priya Sharma | 2024-01-22 | Completed
2 | No extra spaces in text fields | LEN(TRIM(A2))=LEN(A2) is TRUE for all rows | Rahul Mehta | 2024-01-22 | Completed
3 | Consistent text casing | Unique values in category cols match expected list | Neha Joshi | 2024-02-05 | Completed
4 | All dates are true date serials | ISNUMBER(A2)=TRUE for all date cells | Amit Roy | 2024-02-05 | Completed
5 | No unexpected blank cells | COUNTBLANK returns 0 for all mandatory columns | Sunita Verma | 2024-02-19 | Completed
6 | All numeric fields are numbers | ISNUMBER returns TRUE; no left-aligned numbers | Karan Malhotra | 2024-03-07 | In Progress
7 | Category labels standardised | Pivot on category col; unique count matches expected | Siddharth Rao | 2024-03-21 | In Progress
8 | No out-of-range values | MIN and MAX match expected bounds for each numeric col | Pooja Iyer | 2024-03-21 | Not Started
9 | Data formatted as Excel Table | Ctrl+T applied — enables dynamic named ranges | Deepa Krishnan | 2024-04-05 | Not Started
10 | Backup of raw data retained | Original sheet or workbook copy preserved before cleaning | Vikram Nair | 2024-01-01 | Completed
💡 PRO TIP: Always convert your clean dataset into an Excel Table (Ctrl+T) before building PivotTables or charts. Tables expand automatically when new rows are added, keeping your dashboard up to date without manual range updates.
STATUS SUMMARY | Count
Completed | 5
In Progress | 2
Not Started | 3