## Project Overview
EXCEL DASHBOARD ¦ Project Management Gantt Chart & Resource Planner
KEY PROJECT METRICS
Total Techniques | Completed | In Progress | Not Started | Overall Progress
120 | 0 | 97 | 23 | 0%
QUICK NAVIGATION — CLICK TO JUMP TO ANY SHEET
Sheet Name | Type | Description | [7 empty] | Click to Open
Raw Data (153 rows) | DATA | ⚠ 150 uncleaned records — messy names, dates, revenue & formats | [7 empty] | → Open Raw Data (153 rows)
Cleaned Data (153 rows) | DATA | ✔ 150 standardised & validated records with cleaning flags | [7 empty] | → Open Cleaned Data (153 rows)
Gantt Chart | PLAN | 📅 Full 26-week Gantt across 4 phases with colour-coded bars | [7 empty] | → Open Gantt Chart
Resource Planner | TEAM | 👥 2-person team: allocation, utilisation & workload by phase | [7 empty] | → Open Resource Planner
Task Tracker | TRACK | ✅ Detailed task log with formulas, dependencies & review dates | [7 empty] | → Open Task Tracker
Data Reference | REF | 📖 Before/after raw→clean examples for all 10 techniques | [7 empty] | → Open Data Reference
Formula Cheat Sheet | REF | 🔢 20 key cleaning formulas with syntax, notes & technique map | [7 empty] | → Open Formula Cheat Sheet
Dashboard Checklist | QA | 📋 10-point pre-deployment quality gate with status tracking | [7 empty] | → Open Dashboard Checklist
10 DATA CLEANING TECHNIQUES — OVERVIEW
No. | Technique | Problem Solved |  |  | ▶ Live Formula (click me!) | Sample Input | Phase | Priority | Status
1 | Remove Duplicates — CRM Export Cleaning | CRM Export Cleaning |  |  | FALSE | ORD-1001 | Phase 1 | Critical | Completed
2 | Trim Extra Spaces — Customer Name Import | Customer Name Import |  |  | Priya Sharma | Priya Sharma | Phase 1 | Critical | Completed
3 | Standardize Text Case — Region Codes | Region Codes |  |  | North West | north west | Phase 1 | High | Completed
4 | Fix Date Formats — Legacy System Dates | Legacy System Dates |  |  | 45320 | 2024-01-29 | Phase 2 | Critical | Completed
5 | Handle Missing Values — Customer Database | Customer Database |  |  | Unknown |  | Phase 2 | High | Completed
6 | Split Combined Columns — Contact Database | Contact Database |  |  | Karan | Karan Malhotra | Phase 2 | Medium | In Progress
7 | Remove Non-Numeric Chars — Revenue Data | Revenue Data |  |  | 150000 | Rs. 1,50,000 | Phase 3 | Critical | In Progress
8 | Validate Data Ranges — HR Age Dataset | HR Age Dataset |  |  | Valid | 45 | Phase 3 | High | Not Started
9 | Standardize Category Labels — Product SKU | Product SKU |  |  | Electronics | electronics | Phase 3 | High | Not Started
10 | Combine & Reconcile Columns — Address | Address |  |  | 123 Main St, Mumbai, 400001 | 123 Main St | Phase 4 | Medium | Not Started

## Raw Data
⚠ RAW DATA — 153 Records (Uncleaned with Null/Wrong Values) ¦ Project Management Dashboard
← Back to Project Overview
# | Task / Technique | Phase | Assigned To | Department | Start Date | End Date | Duration (Days) | Status | % Complete | Priority | Daily Rate (₹) | Hours | Revenue (Raw) | Notes
1 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Sunita Verma | BI & Analytics | 2024-02-06 |  |  | In Progress | 40 | Low | 3000 |  |  | —
2 | Trim Extra Spaces — Customer Name Import | PHASE 2 | deepa krishnan | business intel. | 2024-05-15 |  |  | Completed | 100.00% | LOW | ₹4200 |  |  | —
3 | Standardize Text Case — Region Codes | Phase 3 | Amit Roy | DATA PLATFORM | 01/25/2024 |  |  | In Progress | 25 | high | ₹4200 |  |  | —
4 | Fix Date Formats — Legacy System Dates | PHASE4 | neha joshi | QUALITY ASSUR. | 2024-03-17 |  |  | Not Started | 0 | CRITICAL | ₹2,000 |  |  | —
5 | Handle Missing Values — Customer Database | PHASE1 | Deepa Krishnan | PMO | 15-05-2024 |  |  | Completed | 100 % | high | INR 5,500 |  |  | —
6 | Split Combined Columns — Contact Database | phase 2 | DEEPA KRISHNAN | BI & ANALYTICS | 2024-02-08 |  |  | In Progress | 25.00% | CRITICAL | Rs. 3,500 |  |  | Extra spaces detected
7 | Trim Extra Spaces — Customer Name Import | PHASE 2 |  | business intel. | 2024-05-15 |  |  | Completed | 100.00% | LOW | ₹4200 |  |  | —
8 | Validate Data Ranges — HR Age Dataset | PHASE4 | Siddharth Rao | biz intel | 02/18/2024 |  |  | Completed | 100.00% | Low | Rs. 4,000 |  |  | —
9 | Standardize Category Labels — Product SKU | PHASE 1 | Meera Pillai | Quality Assur. | 32/13/2024 |  |  | In Progress | 50.00% | low | Rs.5000 |  |  | Re-run TRIM
10 | duplicate cleanup | PHASE2 | Rohit Gupta | pmo | 2024-01-19 |  |  | In Progress | 75.00% | medium | Rs. 3,500 |  |  | —
11 | Remove Duplicates — CRM Export Cleaning | phase-2 | Meera Pillai | BI & Analytics | 2024-05-07 |  |  | In Progress | 25% | Low | 3000 |  |  | Awaiting sign-off
12 | Trim Extra Spaces — Customer Name Import | PHASE 4 | Lakshmi Nair | BUSINESS INTEL. | 2024-04-22 | 2024-02-01 | -81 | Not Started | 0% | Medium | Rs.5000 | -648 | #VALUE! | Check formula
13 | Standardize Text Case — Region Codes | PHASE1 | 12345 | data platform | 22-02-2024 |  |  | Completed | 100 | MEDIUM | Rs.5000 |  |  | Needs validation
14 |  | Phase 2 | Priya Sharma | QUALITY ASSUR. | 01/27/2024 |  | 28 | completed | 0 % | MEDIUM | Rs.5000 | TBD | Rs.514492 | Check formula
15 | Handle Missing Values — Customer Database | PHASE 3 | RAHUL MEHTA |  | 02/20/2024 |  |  | In Progress | 25 % | CRITICAL | 3000 |  |  | Verified OK
16 | Split Combined Columns — Contact Database | Phase 4 | Rahul Mehta | BI & ANALYTICS | Not Available |  |  | In Progress | 25.00% | high | INR 5,500 |  |  | Extra spaces detected
17 | Remove Non-Numeric Chars — Revenue Data | PH 5 | SUNITA VERMA | Business Intel. | 2024-01-21 |  |  | Not Started | 0 | HIGH | Rs. 4,000 |  |  | Pending review
18 | Validate Data Ranges — HR Age Dataset | PHASE2 | Vikram Nair | data platform | 02/06/2024 |  |  | In Progress | 75% | high | Rs. 4,000 |  |  | —
19 | Standardize Category Labels — Product SKU | PHASE3 | NEHA JOSHI | QUALITY ASSUR. | 18-04-2024 |  |  | Not Started | 0 | CRITICAL | ₹4200 |  |  | Verified OK
20 | Combine & Reconcile Columns — Address | Phase 4 | Arjun Pillai | PMO | 27-03-2024 |  |  | Completed | 100.00% | medium | ₹2,000 |  |  | Needs validation
21 | Remove Duplicates — CRM Export Cleaning | phase 1 | pooja iyer | bi & analytics | 07-05-2024 |  |  | In Progress | 25 | high | ₹4200 |  |  | Check formula
22 | Trim Extra Spaces — Customer Name Import | phase 2 | POOJA IYER | BUSINESS INTEL. | 2024-02-22 |  |  | In Progress | 40 % | critical | 3000 |  |  | —
23 | Split Combined Columns — Contact Database | phase 2 | DEEPA KRISHNAN | BI & ANALYTICS | 2024-02-08 |  |  | In Progress | 25.00% | CRITICAL | Rs. 3,500 |  |  | Extra spaces detected
24 | Fix Date Formats — Legacy System Dates | PHASE4 | Karan Malhotra | QUALITY ASSUR. | 23-03-2024 |  |  | Completed | 100.00% | Critical | Rs. 4,000 |  |  | Needs validation
25 | Handle Missing Values — Customer Database | Phase 1 | rohit gupta | pmo | 01/11/2024 |  |  | In Progress | 40.00% | CRITICAL | Rs.5000 |  |  | Pending review
26 | Split Combined Columns — Contact Database | phase 2 | ananya singh | BI & Analytics | 2024-01-07 |  |  | Not Started | 0.00% | MEDIUM | Rs. 4,000 |  |  | Extra spaces detected
27 | Remove Non-Numeric Chars — Revenue Data | phase 3 | Rohit Gupta | BUSINESS INTEL. | 2024-05-23 |  |  | Completed | 100 | high | ₹4200 |  |  | Extra spaces detected
28 | Validate Data Ranges — HR Age Dataset | phase 4 | ANANYA SINGH | DATA PLATFORM | 2024-05-15 |  |  | Completed | 100% | Low | ₹2,000 |  |  | Flag for QA
29 | Standardize Category Labels — Product SKU | Phase 1 | Priya Sharma | Quality Assur. | 05/01/2024 |  |  | In Progress | 75.00% | High | Rs. 3,500 |  |  | Pending review
30 | Combine & Reconcile Columns — Address | phase 2 | Priya Sharma | pmo | 05/11/2024 |  |  | In Progress | 50 | CRITICAL | 3000 |  |  | Check formula
31 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Priya Sharma | bi & analytics | 03/15/2024 |  |  | Completed | 100% | MEDIUM | INR 5,500 |  |  | Flag for QA
32 | Trim Extra Spaces — Customer Name Import | phase 4 | Vikram Nair | Business Intel. | 2024-04-22 |  |  | Completed | 100 | Critical | Rs. 4,000 |  |  | Check formula
33 | Standardize Text Case — Region Codes | PHASE1 | vikram nair | Data Platform | 2024-02-16 |  |  | In Progress | 25 % | CRITICAL | Rs. 3,500 |  |  | Extra spaces detected
34 | Fix Date Formats — Legacy System Dates | phase 2 | Arjun Pillai | QUALITY ASSUR. | 01/01/2024 |  |  | Completed | 100.00% | CRITICAL | ₹2,000 |  |  | —
35 | Handle Missing Values — Customer Database | PHASE 3 | neha joshi | PMO | 2024-02-28 |  |  | In Progress | 40.00% | High | ₹2,000 |  |  | —
36 | Split Combined Columns — Contact Database | PHASE4 | pooja iyer | BI & Analytics | 05/23/2024 |  |  | In Progress | 65 | medium | Rs. 3,500 |  |  | Flag for QA
37 | Remove Non-Numeric Chars — Revenue Data | phase 1 | POOJA IYER | business intel. | 11-03-2024 |  |  | Not Started | 0 % | High | Rs. 3,500 |  |  | Extra spaces detected
38 | Validate Data Ranges — HR Age Dataset | PHASE2 | Pooja Iyer | DATA PLATFORM | 17-03-2024 |  |  | In Progress | 50.00% | low | 3000 |  |  | Minor inconsistency
39 | Standardize Category Labels — Product SKU | PHASE 3 | siddharth rao | QUALITY ASSUR. | 04/28/2024 |  |  | In Progress | 75 % | low | Rs. 3,500 |  |  | —
40 | Combine & Reconcile Columns — Address | PHASE 4 | Siddharth Rao | PMO | 03/21/2024 |  |  | In Progress | 25 | MEDIUM | ₹4200 |  |  | Extra spaces detected
41 | Remove Duplicates — CRM Export Cleaning | phase 1 | Lakshmi Nair | BI & Analytics | 17-01-2024 |  |  | In Progress | 50 % | CRITICAL | ₹2,000 |  |  | —
42 | Trim Extra Spaces — Customer Name Import | PHASE 2 | Lakshmi Nair | Business Intel. | 01-05-2024 |  |  | In Progress | 25% | LOW | INR 5,500 |  |  | Minor inconsistency
43 | Standardize Text Case — Region Codes | PHASE 3 | ROHIT GUPTA | data platform | 2024-01-09 |  |  | In Progress | 40% | High | 3000 |  |  | —
44 | Fix Date Formats — Legacy System Dates | PHASE 4 | amit roy | quality assur. | 02/16/2024 |  |  | Not Started | 0 | LOW | Rs. 4,000 |  |  | Needs validation
45 | Handle Missing Values — Customer Database | PHASE1 | SUNITA VERMA | pmo | 06-04-2024 |  |  | Completed | 100% | Low | ₹4200 |  |  | Re-run TRIM
46 | Split Combined Columns — Contact Database | Phase 2 | Vikram Nair | BI & Analytics | 2024-05-17 |  |  | In Progress | 25 % | LOW | ₹2,000 |  |  | Minor inconsistency
47 | Remove Non-Numeric Chars — Revenue Data | PHASE 3 | RAHUL MEHTA | BUSINESS INTEL. | 01/25/2024 |  |  | Completed | 100.00% | medium | Rs. 3,500 |  |  | Extra spaces detected
48 | Validate Data Ranges — HR Age Dataset | PHASE 4 | Amit Roy | Data Platform | 02/12/2024 |  |  | In Progress | 25.00% | medium | Rs.5000 |  |  | Awaiting sign-off
49 | Standardize Category Labels — Product SKU | PHASE1 | ARJUN PILLAI | QUALITY ASSUR. | 2024-03-25 |  |  | In Progress | 25 % | MEDIUM | INR 5,500 |  |  | Extra spaces detected
50 | Combine & Reconcile Columns — Address | phase 2 | Arjun Pillai | PMO | 17-01-2024 |  |  | In Progress | 75.00% | high | ₹2,000 |  |  | Minor inconsistency
51 | Remove Duplicates — CRM Export Cleaning | PHASE3 | Deepa Krishnan | bi & analytics | 05/15/2024 |  |  | In Progress | 40 | Critical | 3000 |  |  | Needs validation
52 | Trim Extra Spaces — Customer Name Import | PHASE4 | Neha Joshi | BUSINESS INTEL. | 2024-01-09 |  |  | Not Started | 0% | MEDIUM | ₹4200 |  |  | —
53 | Standardize Text Case — Region Codes | PHASE1 | MEERA PILLAI | Data Platform | 03/19/2024 |  |  | In Progress | 40.00% | low | ₹2,000 |  |  | —
54 | Fix Date Formats — Legacy System Dates | Phase 2 | Pooja Iyer | quality assur. | 07-03-2024 |  |  | In Progress | 65.00% | CRITICAL | 3000 |  |  | Pending review
55 | Handle Missing Values — Customer Database | phase 3 | ananya singh | pmo | 2024-04-02 |  |  | Completed | 100% | low | ₹2,000 |  |  | Pending review
56 | Split Combined Columns — Contact Database | PHASE4 | siddharth rao | BI & ANALYTICS | 17-01-2024 |  |  | Not Started | 0 % | High | ₹4200 |  |  | Verified OK
57 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | meera pillai | business intel. | 26-06-2024 |  |  | In Progress | 25.00% | Critical | ₹4200 |  |  | —
58 | Validate Data Ranges — HR Age Dataset | Phase 2 | Lakshmi Nair | data platform | 04/10/2024 |  |  | Not Started | 0 | CRITICAL | ₹4200 |  |  | Check formula
59 | Standardize Category Labels — Product SKU | PHASE 3 | Rohit Gupta | Quality Assur. | 2024-05-17 |  |  | In Progress | 65.00% | Low | ₹2,000 |  |  | Minor inconsistency
60 | Combine & Reconcile Columns — Address | phase 4 | Priya Sharma | PMO | 2024-02-28 |  |  | Not Started | 0.00% | Critical | Rs.5000 |  |  | Verified OK
61 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Amit Roy | BI & Analytics | 18-06-2024 |  |  | In Progress | 40 | critical | ₹2,000 |  |  | Pending review
62 | Trim Extra Spaces — Customer Name Import | PHASE 2 | AMIT ROY | business intel. | 2024-05-25 |  |  | In Progress | 75.00% | High | 3000 |  |  | Needs validation
63 | Standardize Text Case — Region Codes | phase 3 | Vikram Nair | Data Platform | 02/10/2024 |  |  | In Progress | 75 % | high | INR 5,500 |  |  | Needs validation
64 | Fix Date Formats — Legacy System Dates | Phase 4 | Vikram Nair | quality assur. | 2024-03-11 |  |  | In Progress | 65% | High | ₹2,000 |  |  | Verified OK
65 | Handle Missing Values — Customer Database | phase 1 | vikram nair | PMO | 02-02-2024 |  |  | In Progress | 25% | Critical | Rs. 4,000 |  |  | Pending review
66 | Split Combined Columns — Contact Database | PHASE2 | Neha Joshi | bi & analytics | 01/03/2024 |  |  | In Progress | 50 % | Medium | 3000 |  |  | Flag for QA
67 | Remove Non-Numeric Chars — Revenue Data | PHASE3 | Karan Malhotra | Business Intel. | 2024-02-12 |  |  | In Progress | 75 % | low | 3000 |  |  | Needs validation
68 | Validate Data Ranges — HR Age Dataset | PHASE4 | NEHA JOSHI | data platform | 2024-05-19 |  |  | In Progress | 75 | Critical | Rs. 3,500 |  |  | Needs validation
69 | Standardize Category Labels — Product SKU | Phase 1 | ANANYA SINGH | Quality Assur. | 01/21/2024 |  |  | In Progress | 40 | MEDIUM | Rs. 4,000 |  |  | Needs validation
70 | Combine & Reconcile Columns — Address | PHASE2 | ROHIT GUPTA | PMO | 2024-04-06 |  |  | In Progress | 25 | Low | Rs. 3,500 |  |  | Re-run TRIM
71 | Remove Duplicates — CRM Export Cleaning | phase 3 | ANANYA SINGH | BI & Analytics | 01/11/2024 |  |  | In Progress | 25 % | Low | ₹2,000 |  |  | —
72 | Trim Extra Spaces — Customer Name Import | PHASE4 | rohit gupta | Business Intel. | 04-04-2024 |  |  | In Progress | 65% | HIGH | ₹2,000 |  |  | Awaiting sign-off
73 | Standardize Text Case — Region Codes | PHASE1 | Lakshmi Nair | DATA PLATFORM | 2024-04-10 |  |  | Not Started | 0.00% | medium | ₹4200 |  |  | Check formula
74 | Fix Date Formats — Legacy System Dates | PHASE2 | Lakshmi Nair | Quality Assur. | 2024-04-28 |  |  | Completed | 100% | medium | Rs.5000 |  |  | Verified OK
75 | Handle Missing Values — Customer Database | phase 3 | Amit Roy | PMO | 10-02-2024 |  |  | In Progress | 40 % | Critical | INR 5,500 |  |  | Flag for QA
76 | Split Combined Columns — Contact Database | PHASE4 | Rahul Mehta | BI & ANALYTICS | 21-05-2024 |  |  | In Progress | 50 | High | Rs. 3,500 |  |  | Minor inconsistency
77 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | RAHUL MEHTA | BUSINESS INTEL. | 13-03-2024 |  |  | In Progress | 25 | MEDIUM | INR 5,500 |  |  | Extra spaces detected
78 | Validate Data Ranges — HR Age Dataset | phase 2 | SUNITA VERMA | data platform | 02/24/2024 |  |  | Completed | 100.00% | medium | 3000 |  |  | Extra spaces detected
79 | Standardize Category Labels — Product SKU | PHASE3 | arjun pillai | QUALITY ASSUR. | 09-01-2024 |  |  | In Progress | 75 | Critical | INR 5,500 |  |  | —
80 | Combine & Reconcile Columns — Address | Phase 4 | KARAN MALHOTRA | PMO | 06/14/2024 |  |  | Not Started | 0 | High | 3000 |  |  | Check formula
81 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Arjun Pillai | BI & ANALYTICS | 18-02-2024 |  |  | In Progress | 75% | Critical | 3000 |  |  | —
82 | Trim Extra Spaces — Customer Name Import | PHASE2 | Siddharth Rao | BUSINESS INTEL. | 01/13/2024 |  |  | In Progress | 40% | medium | Rs. 4,000 |  |  | —
83 | Standardize Text Case — Region Codes | phase 3 | KARAN MALHOTRA | Data Platform | 2024-04-08 |  |  | In Progress | 65.00% | Low | Rs.5000 |  |  | Extra spaces detected
84 | Fix Date Formats — Legacy System Dates | PHASE 4 | Siddharth Rao | QUALITY ASSUR. | 06/10/2024 |  |  | In Progress | 65 | low | ₹4200 |  |  | Extra spaces detected
85 | Handle Missing Values — Customer Database | Phase 1 | siddharth rao | pmo | 19-05-2024 |  |  | In Progress | 75 % | High | ₹4200 |  |  | Awaiting sign-off
86 | Split Combined Columns — Contact Database | phase 2 | meera pillai | bi & analytics | 04-04-2024 |  |  | In Progress | 50 | low | 3000 |  |  | Flag for QA
87 | Remove Non-Numeric Chars — Revenue Data | PHASE3 | Meera Pillai | business intel. | 2024-01-19 |  |  | In Progress | 65% | Medium | INR 5,500 |  |  | Flag for QA
88 | Validate Data Ranges — HR Age Dataset | PHASE4 | Ananya Singh | Data Platform | 2024-05-25 |  |  | In Progress | 50% | Critical | INR 5,500 |  |  | Re-run TRIM
89 | Standardize Category Labels — Product SKU | phase 1 | Rohit Gupta | Quality Assur. | 02/16/2024 |  |  | Not Started | 0 | medium | Rs. 4,000 |  |  | Check formula
90 | Combine & Reconcile Columns — Address | Phase 2 | Rahul Mehta | PMO | 05/15/2024 |  |  | In Progress | 40.00% | Critical | Rs. 3,500 |  |  | Minor inconsistency
91 | Remove Duplicates — CRM Export Cleaning | PHASE3 | PRIYA SHARMA | bi & analytics | 07-03-2024 |  |  | In Progress | 75 | low | ₹2,000 |  |  | —
92 | Trim Extra Spaces — Customer Name Import | phase 4 | Sunita Verma | BUSINESS INTEL. | 2024-05-27 |  |  | In Progress | 25.00% | Critical | INR 5,500 |  |  | —
93 | Standardize Text Case — Region Codes | PHASE1 | Arjun Pillai | DATA PLATFORM | 03/19/2024 |  |  | Not Started | 0% | LOW | ₹2,000 |  |  | Awaiting sign-off
94 | Fix Date Formats — Legacy System Dates | PHASE2 | deepa krishnan | quality assur. | 02/24/2024 |  |  | Completed | 100% | critical | INR 5,500 |  |  | Re-run TRIM
95 | Handle Missing Values — Customer Database | Phase 3 | KARAN MALHOTRA | PMO | 02/18/2024 |  |  | In Progress | 75 % | HIGH | INR 5,500 |  |  | —
96 | Split Combined Columns — Contact Database | PHASE 4 | Arjun Pillai | bi & analytics | 21-01-2024 |  |  | In Progress | 65 % | HIGH | ₹2,000 |  |  | Needs validation
97 | Remove Non-Numeric Chars — Revenue Data | PHASE 1 | Siddharth Rao | business intel. | 10-06-2024 |  |  | In Progress | 25.00% | CRITICAL | Rs. 4,000 |  |  | —
98 | Validate Data Ranges — HR Age Dataset | Phase 2 | meera pillai | DATA PLATFORM | 2024-05-07 |  |  | In Progress | 65 | low | Rs. 4,000 |  |  | Verified OK
99 | Standardize Category Labels — Product SKU | phase 3 | ananya singh | QUALITY ASSUR. | 03-01-2024 |  |  | In Progress | 65.00% | Low | Rs. 4,000 |  |  | Check formula
100 | Combine & Reconcile Columns — Address | PHASE4 | Pooja Iyer | PMO | 2024-02-18 |  |  | In Progress | 25 % | High | ₹2,000 |  |  | —
101 | Remove Duplicates — CRM Export Cleaning | PHASE1 | Ananya Singh | BI & Analytics | 02/26/2024 |  |  | In Progress | 40.00% | low | Rs.5000 |  |  | Check formula
102 | Trim Extra Spaces — Customer Name Import | Phase 2 | ROHIT GUPTA | Business Intel. | 15-01-2024 |  |  | In Progress | 50.00% | LOW | ₹4200 |  |  | —
103 | Standardize Text Case — Region Codes | PHASE3 | Priya Sharma | Data Platform | 28-02-2024 |  |  | In Progress | 75 % | Low | Rs.5000 |  |  | Pending review
104 | Fix Date Formats — Legacy System Dates | phase 4 | Amit Roy | Quality Assur. | 2024-06-18 |  |  | In Progress | 65.00% | HIGH | ₹2,000 |  |  | Check formula
105 | Handle Missing Values — Customer Database | PHASE1 | Amit Roy | PMO | 04-02-2024 |  |  | Not Started | 0% | CRITICAL | Rs.5000 |  |  | Needs validation
106 | Split Combined Columns — Contact Database | PHASE 2 | Rahul Mehta | BI & Analytics | 05/19/2024 |  |  | Not Started | 0.00% | CRITICAL | ₹2,000 |  |  | —
107 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | deepa krishnan | BUSINESS INTEL. | 2024-03-17 |  |  | In Progress | 75% | MEDIUM | Rs. 3,500 |  |  | Pending review
108 | Validate Data Ranges — HR Age Dataset | Phase 4 | Sunita Verma | DATA PLATFORM | 01/03/2024 |  |  | Completed | 100.00% | Critical | ₹2,000 |  |  | —
109 | Standardize Category Labels — Product SKU | PHASE 1 | Deepa Krishnan | QUALITY ASSUR. | 2024-06-14 |  |  | In Progress | 75.00% | low | Rs. 4,000 |  |  | Flag for QA
110 | Combine & Reconcile Columns — Address | PHASE2 | KARAN MALHOTRA | PMO | 28-02-2024 |  |  | Not Started | 0 | LOW | 3000 |  |  | Needs validation
111 | Remove Duplicates — CRM Export Cleaning | PHASE 3 | deepa krishnan | bi & analytics | 12-02-2024 |  |  | In Progress | 25.00% | high | Rs.5000 |  |  | Re-run TRIM
112 | Trim Extra Spaces — Customer Name Import | Phase 4 | Neha Joshi | Business Intel. | 2024-04-12 |  |  | Completed | 100.00% | critical | Rs. 4,000 |  |  | —
113 | Standardize Text Case — Region Codes | PHASE1 | Neha Joshi | data platform | 2024-01-09 |  |  | Completed | 100 % | LOW | Rs.5000 |  |  | Needs validation
114 | Fix Date Formats — Legacy System Dates | PHASE2 | Meera Pillai | Quality Assur. | 2024-01-27 |  |  | In Progress | 50.00% | critical | ₹4200 |  |  | Flag for QA
115 | Handle Missing Values — Customer Database | PHASE3 | Siddharth Rao | PMO | 10-02-2024 |  |  | In Progress | 25% | Low | Rs. 4,000 |  |  | Minor inconsistency
116 | Split Combined Columns — Contact Database | phase 4 | Ananya Singh | BI & ANALYTICS | 17-05-2024 |  |  | In Progress | 50.00% | LOW | Rs. 4,000 |  |  | Check formula
117 | Remove Non-Numeric Chars — Revenue Data | PHASE1 | ROHIT GUPTA | BUSINESS INTEL. | 03/05/2024 |  |  | In Progress | 40.00% | Critical | 3000 |  |  | Verified OK
118 | Validate Data Ranges — HR Age Dataset | phase 2 | rohit gupta | DATA PLATFORM | 01-01-2024 |  |  | In Progress | 25 | medium | ₹2,000 |  |  | Re-run TRIM
119 | Standardize Category Labels — Product SKU | phase 3 | PRIYA SHARMA | QUALITY ASSUR. | 15-05-2024 |  |  | Completed | 100.00% | MEDIUM | ₹4200 |  |  | Flag for QA
120 | Combine & Reconcile Columns — Address | Phase 4 | Lakshmi Nair | PMO | 28-06-2024 |  |  | Completed | 100.00% | High | INR 5,500 |  |  | —
121 | Remove Duplicates — CRM Export Cleaning | PHASE 1 | SUNITA VERMA | bi & analytics | 2024-03-17 |  |  | In Progress | 50 % | Medium | ₹2,000 |  |  | —
122 | Trim Extra Spaces — Customer Name Import | PHASE 2 | Rahul Mehta | BUSINESS INTEL. | 26-02-2024 |  |  | In Progress | 40 | Medium | ₹4200 |  |  | —
123 | Standardize Text Case — Region Codes | PHASE3 | ARJUN PILLAI | Data Platform | 01-05-2024 |  |  | In Progress | 25% | medium | Rs.5000 |  |  | Verified OK
124 | Fix Date Formats — Legacy System Dates | phase 4 | SUNITA VERMA | quality assur. | 01/13/2024 |  |  | In Progress | 40 % | low | Rs. 3,500 |  |  | Flag for QA
125 | Handle Missing Values — Customer Database | phase 1 | vikram nair | PMO | 2024-06-26 |  |  | In Progress | 75 % | CRITICAL | ₹4200 |  |  | —
126 | Split Combined Columns — Contact Database | phase 2 | Deepa Krishnan | bi & analytics | 2024-05-13 |  |  | In Progress | 25 % | CRITICAL | Rs. 3,500 |  |  | Verified OK
127 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | neha joshi | Business Intel. | 05/25/2024 |  |  | In Progress | 65.00% | LOW | 3000 |  |  | Flag for QA
128 | Validate Data Ranges — HR Age Dataset | phase 4 | KARAN MALHOTRA | Data Platform | 2024-03-27 |  |  | In Progress | 75.00% | Critical | ₹2,000 |  |  | Needs validation
129 | Standardize Category Labels — Product SKU | PHASE 1 | karan malhotra | QUALITY ASSUR. | 04/20/2024 |  |  | In Progress | 75 % | MEDIUM | Rs.5000 |  |  | —
130 | Combine & Reconcile Columns — Address | Phase 2 | Meera Pillai | PMO | 01/19/2024 |  |  | In Progress | 25.00% | CRITICAL | Rs. 3,500 |  |  | Awaiting sign-off
131 | Remove Duplicates — CRM Export Cleaning | phase 3 | Rohit Gupta | BI & ANALYTICS | 2024-05-25 |  |  | In Progress | 75 | LOW | 3000 |  |  | Flag for QA
132 | Trim Extra Spaces — Customer Name Import | PHASE4 | rohit gupta | BUSINESS INTEL. | 14-04-2024 |  |  | In Progress | 65 % | LOW | Rs.5000 |  |  | Check formula
133 | Standardize Text Case — Region Codes | Phase 1 | RAHUL MEHTA | Data Platform | 06/08/2024 |  |  | In Progress | 65 | critical | ₹4200 |  |  | Verified OK
134 | Fix Date Formats — Legacy System Dates | PHASE 2 | Lakshmi Nair | QUALITY ASSUR. | 04/22/2024 |  |  | In Progress | 50 % | high | 3000 |  |  | Check formula
135 | Handle Missing Values — Customer Database | Phase 3 | Lakshmi Nair | pmo | 2024-06-06 |  |  | In Progress | 25% | Medium | INR 5,500 |  |  | Verified OK
136 | Split Combined Columns — Contact Database | phase 4 | Sunita Verma | bi & analytics | 03/07/2024 |  |  | In Progress | 50% | HIGH | Rs. 4,000 |  |  | Verified OK
137 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Sunita Verma | business intel. | 26-02-2024 |  |  | In Progress | 50% | MEDIUM | Rs. 4,000 |  |  | —
138 | Validate Data Ranges — HR Age Dataset | Phase 2 | Sunita Verma | data platform | 2024-02-14 |  |  | In Progress | 50% | HIGH | ₹2,000 |  |  | —
139 | Standardize Category Labels — Product SKU | phase 3 | Neha Joshi | Quality Assur. | 14-04-2024 |  |  | In Progress | 25% | medium | 3000 |  |  | Awaiting sign-off
140 | Combine & Reconcile Columns — Address | PHASE 4 | Karan Malhotra | pmo | 2024-01-21 |  |  | In Progress | 65 % | critical | Rs. 3,500 |  |  | —
141 | Remove Duplicates — CRM Export Cleaning | PHASE1 | POOJA IYER | BI & ANALYTICS | 02-04-2024 |  |  | In Progress | 40 % | high | 3000 |  |  | Pending review
142 | Trim Extra Spaces — Customer Name Import | phase 2 | siddharth rao | BUSINESS INTEL. | 2024-04-22 |  |  | Completed | 100 | Critical | ₹2,000 |  |  | —
143 | Standardize Text Case — Region Codes | Phase 3 | Meera Pillai | data platform | 18-06-2024 |  |  | In Progress | 50 | medium | INR 5,500 |  |  | —
144 | Fix Date Formats — Legacy System Dates | Phase 4 | ANANYA SINGH | Quality Assur. | 03/25/2024 |  |  | In Progress | 75% | low | 3000 |  |  | Check formula
145 | Handle Missing Values — Customer Database | PHASE 1 | Rohit Gupta | pmo | 04/18/2024 |  |  | In Progress | 25% | low | Rs. 3,500 |  |  | —
146 | Split Combined Columns — Contact Database | PHASE2 | Lakshmi Nair | bi & analytics | 27-03-2024 |  |  | In Progress | 75 % | critical | Rs. 3,500 |  |  | Verified OK
147 | Remove Non-Numeric Chars — Revenue Data | phase 3 | Meera Pillai | Business Intel. | 04/20/2024 |  |  | In Progress | 75% | Medium | ₹2,000 |  |  | —
148 | Validate Data Ranges — HR Age Dataset | PHASE 4 | ROHIT GUPTA | Data Platform | 01/25/2024 |  |  | Completed | 100 | low | Rs. 4,000 |  |  | Re-run TRIM
149 | Standardize Category Labels — Product SKU | Phase 1 | rohit gupta | QUALITY ASSUR. | 27-03-2024 |  |  | Not Started | 0 % | Low | ₹4200 |  |  | Pending review
150 | Combine & Reconcile Columns — Address | phase 2 | lakshmi nair | pmo | 2024-06-18 |  |  | Not Started | 0 | HIGH | ₹2,000 |  |  | Needs validation

## Cleaned Data
✔ CLEANED DATA — 120 Records (Standardised & Validated) ¦ Project Management Dashboard
← Back to Project Overview
# | Task / Technique | Phase | Assigned To | Department | Start Date | End Date | Duration (Days) | Status | % Complete | Priority | Daily Rate (₹) | Hours | Revenue (₹) | Notes | Flag
1 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Rahul Mehta | BI & Analytics | 2024-03-24 | 2024-04-03 | 10 | In Progress | 100% | High | 2000 | 140 | 20000 | Extra spaces detected | In Progress
2 | Trim Extra Spaces — Customer Name Import | Phase 2 | Sunita Verma | Business Intel. | 2024-05-08 | 2024-05-15 | 7 | In Progress | 100% | Critical | 4000 | 100 | 28000 | Extra spaces detected | In Progress
3 | Standardize Text Case — Region Codes | Phase 3 | Sunita Verma | Data Platform | 2024-02-16 | 2024-02-28 | 12 | Not Started | 0% | Critical | 4200 | 140 | 50400 | — | Not Started
4 | Fix Date Formats — Legacy System Dates | Phase 4 | Sunita Verma | Quality Assur. | 2024-02-19 | 2024-02-26 | 7 | In Progress | 75% | High | 4200 | 0 | 29400 | Pending review | In Progress
5 | Handle Missing Values — Customer Database | Phase 1 | Arjun Pillai | PMO | 2024-02-24 | 2024-03-23 | 28 | Not Started | 0% | Critical | 4200 | 0 | 117600 | Pending review | Not Started
6 | Split Combined Columns — Contact Database | Phase 2 | Arjun Pillai | BI & Analytics | 2024-05-21 | 2024-05-28 | 7 | In Progress | 100% | Critical | 5500 | 168 | 38500 | Extra spaces detected | In Progress
7 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Karan Malhotra | Business Intel. | 2024-04-30 | 2024-05-14 | 14 | In Progress | 100% | High | 5500 | 168 | 77000 | — | In Progress
8 | Validate Data Ranges — HR Age Dataset | Phase 4 | Karan Malhotra | Data Platform | 2024-01-11 | 2024-02-08 | 28 | Not Started | 0% | Low | 3500 | 0 | 98000 | — | Not Started
9 | Standardize Category Labels — Product SKU | Phase 1 | Siddharth Rao | Quality Assur. | 2024-01-25 | 2024-02-04 | 10 | Not Started | 0% | Critical | 5500 | 0 | 55000 | — | Not Started
10 | Combine & Reconcile Columns — Address | Phase 2 | Pooja Iyer | PMO | 2024-01-16 | 2024-01-30 | 14 | In Progress | 75% | Critical | 2000 | 120 | 28000 | — | In Progress
11 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Meera Pillai | BI & Analytics | 2024-05-01 | 2024-05-08 | 7 | In Progress | 40% | High | 3000 | 80 | 21000 | Check formula | In Progress
12 | Fix Date Formats — Legacy System Dates | Phase 4 | Sunita Verma | Quality Assur. | 2024-02-19 | 2024-02-26 | 7 | In Progress | 75% | High | 4200 | 0 | 29400 | Pending review | In Progress
13 | Standardize Text Case — Region Codes | Phase 1 | Ananya Singh | Data Platform | 2024-04-30 | 2024-05-21 | 21 | In Progress | 65% | Medium | 3500 | 140 | 73500 | Extra spaces detected | In Progress
14 | Fix Date Formats — Legacy System Dates | Phase 2 | Priya Sharma | Quality Assur. | 2024-05-04 | 2024-05-11 | 7 | In Progress | 75% | Critical | 3000 | 60 | 21000 | Pending review | In Progress
15 | Handle Missing Values — Customer Database | Phase 3 | Lakshmi Nair | PMO | 2024-01-22 | 2024-02-05 | 14 | In Progress | 75% | Critical | 4000 | 140 | 56000 | — | In Progress
16 | Split Combined Columns — Contact Database | Phase 4 | Amit Roy | BI & Analytics | 2024-04-12 | 2024-04-22 | 10 | In Progress | 100% | Low | 3500 | 140 | 35000 | Verified OK | In Progress
17 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Rahul Mehta | Business Intel. | 2024-03-12 | 2024-03-24 | 12 | In Progress | 75% | Low | 5500 | 168 | 66000 | — | In Progress
18 | Validate Data Ranges — HR Age Dataset | Phase 2 | Sunita Verma | Data Platform | 2024-04-06 | 2024-05-04 | 28 | Not Started | 0% | Medium | 3500 | 80 | 98000 | Check formula | Not Started
19 | Standardize Category Labels — Product SKU | Phase 3 | Deepa Krishnan | Quality Assur. | 2024-01-13 | 2024-01-23 | 10 | In Progress | 65% | Critical | 2000 | 80 | 20000 | Check formula | In Progress
20 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | PMO | 2024-03-28 | 2024-04-04 | 7 | Not Started | 0% | Low | 5000 | 140 | 35000 | Verified OK | Not Started
21 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Neha Joshi | BI & Analytics | 2024-01-02 | 2024-01-09 | 7 | In Progress | 50% | High | 4000 | 80 | 28000 | — | In Progress
22 | Trim Extra Spaces — Customer Name Import | Phase 2 | Arjun Pillai | Business Intel. | 2024-04-06 | 2024-04-16 | 10 | In Progress | 100% | Medium | 4200 | 140 | 42000 | Check formula | In Progress
23 | Standardize Text Case — Region Codes | Phase 3 | Pooja Iyer | Data Platform | 2024-01-23 | 2024-01-30 | 7 | In Progress | 65% | Low | 5000 | 80 | 35000 | — | In Progress
24 | Fix Date Formats — Legacy System Dates | Phase 4 | Siddharth Rao | Quality Assur. | 2024-05-25 | 2024-06-22 | 28 | In Progress | 50% | Medium | 3000 | 120 | 84000 | — | In Progress
25 | Handle Missing Values — Customer Database | Phase 1 | Siddharth Rao | PMO | 2024-05-22 | 2024-06-01 | 10 | In Progress | 25% | Critical | 5500 | 140 | 55000 | Verified OK | In Progress
26 | Split Combined Columns — Contact Database | Phase 2 | Ananya Singh | BI & Analytics | 2024-04-19 | 2024-04-29 | 10 | In Progress | 100% | Medium | 5000 | 120 | 50000 | Verified OK | In Progress
27 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Meera Pillai | Business Intel. | 2024-02-10 | 2024-02-22 | 12 | In Progress | 100% | High | 3500 | 0 | 42000 | Needs validation | In Progress
28 | Validate Data Ranges — HR Age Dataset | Phase 4 | Ananya Singh | Data Platform | 2024-01-25 | 2024-02-08 | 14 | In Progress | 40% | Critical | 3500 | 100 | 49000 | Needs validation | In Progress
29 | Standardize Category Labels — Product SKU | Phase 1 | Lakshmi Nair | Quality Assur. | 2024-04-20 | 2024-05-11 | 21 | In Progress | 75% | Low | 4000 | 80 | 84000 | — | In Progress
30 | Combine & Reconcile Columns — Address | Phase 2 | Rahul Mehta | PMO | 2024-04-01 | 2024-04-15 | 14 | In Progress | 25% | Low | 4000 | 168 | 56000 | — | In Progress
31 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Rahul Mehta | BI & Analytics | 2024-01-07 | 2024-01-28 | 21 | In Progress | 50% | Medium | 4200 | 0 | 88200 | — | In Progress
32 | Trim Extra Spaces — Customer Name Import | Phase 4 | Rahul Mehta | Business Intel. | 2024-04-09 | 2024-04-21 | 12 | In Progress | 65% | Medium | 5500 | 80 | 66000 | Verified OK | In Progress
33 | Standardize Text Case — Region Codes | Phase 1 | Amit Roy | Data Platform | 2024-04-24 | 2024-05-22 | 28 | Not Started | 0% | High | 4000 | 140 | 112000 | Verified OK | Not Started
34 | Fix Date Formats — Legacy System Dates | Phase 2 | Deepa Krishnan | Quality Assur. | 2024-03-06 | 2024-03-16 | 10 | In Progress | 50% | Medium | 5000 | 60 | 50000 | Pending review | In Progress
35 | Handle Missing Values — Customer Database | Phase 3 | Arjun Pillai | PMO | 2024-04-20 | 2024-04-30 | 10 | In Progress | 50% | Critical | 2000 | 168 | 20000 | Pending review | In Progress
36 | Split Combined Columns — Contact Database | Phase 4 | Deepa Krishnan | BI & Analytics | 2024-04-01 | 2024-04-15 | 14 | In Progress | 50% | Medium | 4200 | 80 | 58800 | Verified OK | In Progress
37 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Arjun Pillai | Business Intel. | 2024-05-29 | 2024-06-26 | 28 | In Progress | 25% | High | 5500 | 120 | 154000 | Verified OK | In Progress
38 | Validate Data Ranges — HR Age Dataset | Phase 2 | Neha Joshi | Data Platform | 2024-05-19 | 2024-06-09 | 21 | In Progress | 40% | High | 5000 | 0 | 105000 | — | In Progress
39 | Standardize Category Labels — Product SKU | Phase 3 | Karan Malhotra | Quality Assur. | 2024-05-19 | 2024-06-02 | 14 | In Progress | 75% | Low | 4000 | 0 | 56000 | Verified OK | In Progress
40 | Combine & Reconcile Columns — Address | Phase 4 | Pooja Iyer | PMO | 2024-05-07 | 2024-05-17 | 10 | In Progress | 75% | Medium | 3500 | 160 | 35000 | Verified OK | In Progress
41 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Meera Pillai | BI & Analytics | 2024-02-28 | 2024-03-06 | 7 | In Progress | 65% | Critical | 3000 | 60 | 21000 | Pending review | In Progress
42 | Trim Extra Spaces — Customer Name Import | Phase 2 | Rohit Gupta | Business Intel. | 2024-04-19 | 2024-04-29 | 10 | In Progress | 75% | Low | 5500 | 120 | 55000 | Verified OK | In Progress
43 | Standardize Text Case — Region Codes | Phase 3 | Ananya Singh | Data Platform | 2024-03-26 | 2024-04-09 | 14 | In Progress | 25% | Low | 4000 | 0 | 56000 | Check formula | In Progress
44 | Fix Date Formats — Legacy System Dates | Phase 4 | Rohit Gupta | Quality Assur. | 2024-01-10 | 2024-01-17 | 7 | In Progress | 40% | Critical | 5500 | 0 | 38500 | — | In Progress
45 | Handle Missing Values — Customer Database | Phase 1 | Lakshmi Nair | PMO | 2024-03-12 | 2024-03-26 | 14 | In Progress | 65% | Critical | 4000 | 60 | 56000 | Verified OK | In Progress
46 | Split Combined Columns — Contact Database | Phase 2 | Priya Sharma | BI & Analytics | 2024-01-27 | 2024-02-06 | 10 | In Progress | 100% | Medium | 3500 | 80 | 35000 | Verified OK | In Progress
47 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Sunita Verma | Business Intel. | 2024-03-06 | 2024-03-13 | 7 | In Progress | 40% | Medium | 4000 | 120 | 28000 | Needs validation | In Progress
48 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | PMO | 2024-03-28 | 2024-04-04 | 7 | Not Started | 0% | Low | 5000 | 140 | 35000 | Verified OK | Not Started
49 | Standardize Category Labels — Product SKU | Phase 1 | Deepa Krishnan | Quality Assur. | 2024-01-08 | 2024-02-05 | 28 | In Progress | 75% | Low | 4000 | 120 | 112000 | — | In Progress
50 | Combine & Reconcile Columns — Address | Phase 2 | Vikram Nair | PMO | 2024-03-20 | 2024-03-27 | 7 | In Progress | 25% | Medium | 5000 | 0 | 35000 | Needs validation | In Progress
51 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Arjun Pillai | BI & Analytics | 2024-01-27 | 2024-02-06 | 10 | Not Started | 0% | Critical | 4200 | 60 | 42000 | Needs validation | Not Started
52 | Trim Extra Spaces — Customer Name Import | Phase 4 | Arjun Pillai | Business Intel. | 2024-04-25 | 2024-05-07 | 12 | In Progress | 25% | High | 5000 | 100 | 60000 | — | In Progress
53 | Standardize Text Case — Region Codes | Phase 1 | Neha Joshi | Data Platform | 2024-03-27 | 2024-04-17 | 21 | In Progress | 100% | High | 5000 | 168 | 105000 | — | In Progress
54 | Fix Date Formats — Legacy System Dates | Phase 2 | Pooja Iyer | Quality Assur. | 2024-01-07 | 2024-01-17 | 10 | In Progress | 65% | Critical | 3000 | 168 | 30000 | Pending review | In Progress
55 | Handle Missing Values — Customer Database | Phase 3 | Meera Pillai | PMO | 2024-02-09 | 2024-03-01 | 21 | In Progress | 65% | Medium | 4200 | 100 | 88200 | Needs validation | In Progress
56 | Split Combined Columns — Contact Database | Phase 4 | Ananya Singh | BI & Analytics | 2024-02-05 | 2024-02-12 | 7 | Not Started | 0% | Critical | 2000 | 168 | 14000 | Needs validation | Not Started
57 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Ananya Singh | Business Intel. | 2024-02-07 | 2024-02-28 | 21 | In Progress | 100% | Low | 2000 | 168 | 42000 | — | In Progress
58 | Validate Data Ranges — HR Age Dataset | Phase 2 | Rohit Gupta | Data Platform | 2024-04-02 | 2024-04-30 | 28 | In Progress | 100% | Critical | 2000 | 120 | 56000 | — | In Progress
59 | Standardize Category Labels — Product SKU | Phase 3 | Priya Sharma | Quality Assur. | 2024-01-25 | 2024-02-06 | 12 | In Progress | 50% | Critical | 5500 | 168 | 66000 | — | In Progress
60 | Combine & Reconcile Columns — Address | Phase 4 | Lakshmi Nair | PMO | 2024-01-08 | 2024-01-20 | 12 | In Progress | 75% | Medium | 3500 | 140 | 42000 | Needs validation | In Progress
61 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Amit Roy | BI & Analytics | 2024-03-12 | 2024-03-24 | 12 | In Progress | 75% | High | 2000 | 0 | 24000 | — | In Progress
62 | Trim Extra Spaces — Customer Name Import | Phase 2 | Sunita Verma | Business Intel. | 2024-03-28 | 2024-04-11 | 14 | In Progress | 75% | Critical | 4200 | 168 | 58800 | Extra spaces detected | In Progress
63 | Standardize Text Case — Region Codes | Phase 3 | Vikram Nair | Data Platform | 2024-05-22 | 2024-06-19 | 28 | Not Started | 0% | High | 4000 | 0 | 112000 | — | Not Started
64 | Fix Date Formats — Legacy System Dates | Phase 4 | Vikram Nair | Quality Assur. | 2024-04-05 | 2024-04-26 | 21 | Not Started | 0% | Critical | 2000 | 120 | 42000 | Needs validation | Not Started
65 | Handle Missing Values — Customer Database | Phase 1 | Vikram Nair | PMO | 2024-04-10 | 2024-04-22 | 12 | In Progress | 75% | Medium | 4000 | 60 | 48000 | — | In Progress
66 | Split Combined Columns — Contact Database | Phase 2 | Deepa Krishnan | BI & Analytics | 2024-01-03 | 2024-01-24 | 21 | Not Started | 0% | Critical | 5500 | 0 | 115500 | Extra spaces detected | Not Started
67 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Neha Joshi | Business Intel. | 2024-03-10 | 2024-03-20 | 10 | In Progress | 40% | High | 3000 | 160 | 30000 | — | In Progress
68 | Validate Data Ranges — HR Age Dataset | Phase 4 | Karan Malhotra | Data Platform | 2024-02-04 | 2024-02-18 | 14 | In Progress | 25% | Low | 2000 | 80 | 28000 | — | In Progress
69 | Standardize Category Labels — Product SKU | Phase 1 | Siddharth Rao | Quality Assur. | 2024-02-24 | 2024-03-16 | 21 | In Progress | 25% | High | 4000 | 80 | 84000 | Check formula | In Progress
70 | Combine & Reconcile Columns — Address | Phase 2 | Pooja Iyer | PMO | 2024-03-30 | 2024-04-09 | 10 | In Progress | 50% | High | 2000 | 60 | 20000 | — | In Progress
71 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Meera Pillai | BI & Analytics | 2024-05-12 | 2024-05-26 | 14 | Not Started | 0% | Critical | 4200 | 140 | 58800 | — | Not Started
72 | Trim Extra Spaces — Customer Name Import | Phase 4 | Meera Pillai | Business Intel. | 2024-01-16 | 2024-01-23 | 7 | In Progress | 50% | High | 2000 | 160 | 14000 | Pending review | In Progress
73 | Standardize Text Case — Region Codes | Phase 1 | Rohit Gupta | Data Platform | 2024-01-03 | 2024-01-24 | 21 | In Progress | 25% | High | 2000 | 80 | 42000 | Verified OK | In Progress
74 | Fix Date Formats — Legacy System Dates | Phase 2 | Rohit Gupta | Quality Assur. | 2024-03-06 | 2024-03-18 | 12 | In Progress | 40% | Low | 3500 | 80 | 42000 | — | In Progress
75 | Handle Missing Values — Customer Database | Phase 3 | Rahul Mehta | PMO | 2024-01-30 | 2024-02-09 | 10 | Not Started | 0% | Medium | 2000 | 60 | 20000 | — | Not Started
76 | Split Combined Columns — Contact Database | Phase 4 | Priya Sharma | BI & Analytics | 2024-05-19 | 2024-06-02 | 14 | In Progress | 40% | High | 5000 | 0 | 70000 | — | In Progress
77 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Rahul Mehta | Business Intel. | 2024-05-14 | 2024-05-21 | 7 | In Progress | 25% | High | 3000 | 100 | 21000 | — | In Progress
78 | Validate Data Ranges — HR Age Dataset | Phase 2 | Vikram Nair | Data Platform | 2024-02-24 | 2024-03-16 | 21 | In Progress | 100% | High | 3500 | 120 | 73500 | Verified OK | In Progress
79 | Standardize Category Labels — Product SKU | Phase 3 | Vikram Nair | Quality Assur. | 2024-01-14 | 2024-01-28 | 14 | In Progress | 40% | Low | 3500 | 100 | 49000 | Extra spaces detected | In Progress
80 | Combine & Reconcile Columns — Address | Phase 4 | Arjun Pillai | PMO | 2024-01-09 | 2024-02-06 | 28 | In Progress | 100% | Low | 3000 | 160 | 84000 | Verified OK | In Progress
81 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Neha Joshi | BI & Analytics | 2024-01-15 | 2024-01-22 | 7 | Not Started | 0% | Critical | 3000 | 160 | 21000 | — | Not Started
82 | Trim Extra Spaces — Customer Name Import | Phase 2 | Neha Joshi | Business Intel. | 2024-02-11 | 2024-02-25 | 14 | In Progress | 75% | Medium | 5000 | 100 | 70000 | Needs validation | In Progress
83 | Standardize Text Case — Region Codes | Phase 3 | Karan Malhotra | Data Platform | 2024-01-18 | 2024-01-30 | 12 | In Progress | 75% | High | 2000 | 0 | 24000 | Pending review | In Progress
84 | Fix Date Formats — Legacy System Dates | Phase 4 | Pooja Iyer | Quality Assur. | 2024-01-17 | 2024-01-31 | 14 | In Progress | 40% | Low | 4200 | 140 | 58800 | Check formula | In Progress
85 | Handle Missing Values — Customer Database | Phase 1 | Siddharth Rao | PMO | 2024-04-12 | 2024-04-26 | 14 | In Progress | 75% | Low | 5000 | 100 | 70000 | — | In Progress
86 | Split Combined Columns — Contact Database | Phase 2 | Meera Pillai | BI & Analytics | 2024-02-02 | 2024-02-23 | 21 | In Progress | 25% | Medium | 3500 | 0 | 73500 | — | In Progress
87 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Rohit Gupta | Business Intel. | 2024-03-22 | 2024-04-12 | 21 | Not Started | 0% | Critical | 5500 | 140 | 115500 | — | Not Started
88 | Validate Data Ranges — HR Age Dataset | Phase 4 | Lakshmi Nair | Data Platform | 2024-03-04 | 2024-03-18 | 14 | In Progress | 50% | Critical | 3000 | 60 | 42000 | Check formula | In Progress
89 | Standardize Category Labels — Product SKU | Phase 1 | Lakshmi Nair | Quality Assur. | 2024-02-28 | 2024-03-13 | 14 | In Progress | 40% | Low | 3000 | 160 | 42000 | Check formula | In Progress
90 | Combine & Reconcile Columns — Address | Phase 2 | Rahul Mehta | PMO | 2024-04-25 | 2024-05-09 | 14 | Not Started | 0% | Medium | 4200 | 0 | 58800 | Needs validation | Not Started
91 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Rahul Mehta | BI & Analytics | 2024-05-10 | 2024-05-22 | 12 | In Progress | 75% | Low | 4000 | 80 | 48000 | Extra spaces detected | In Progress
92 | Trim Extra Spaces — Customer Name Import | Phase 4 | Amit Roy | Business Intel. | 2024-02-23 | 2024-03-22 | 28 | In Progress | 100% | Low | 2000 | 120 | 56000 | — | In Progress
93 | Standardize Text Case — Region Codes | Phase 1 | Sunita Verma | Data Platform | 2024-02-11 | 2024-02-18 | 7 | In Progress | 50% | Critical | 2000 | 100 | 14000 | Needs validation | In Progress
94 | Fix Date Formats — Legacy System Dates | Phase 2 | Vikram Nair | Quality Assur. | 2024-02-01 | 2024-02-13 | 12 | In Progress | 65% | Low | 3000 | 160 | 36000 | Verified OK | In Progress
95 | Handle Missing Values — Customer Database | Phase 3 | Deepa Krishnan | PMO | 2024-05-05 | 2024-05-12 | 7 | Not Started | 0% | Low | 5500 | 140 | 38500 | Needs validation | Not Started
96 | Split Combined Columns — Contact Database | Phase 4 | Neha Joshi | BI & Analytics | 2024-01-28 | 2024-02-25 | 28 | In Progress | 25% | Critical | 2000 | 80 | 56000 | — | In Progress
97 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Karan Malhotra | Business Intel. | 2024-05-05 | 2024-05-19 | 14 | In Progress | 50% | Medium | 4000 | 168 | 56000 | Needs validation | In Progress
98 | Validate Data Ranges — HR Age Dataset | Phase 2 | Karan Malhotra | Data Platform | 2024-05-30 | 2024-06-09 | 10 | In Progress | 40% | High | 3000 | 80 | 30000 | Check formula | In Progress
99 | Standardize Category Labels — Product SKU | Phase 3 | Pooja Iyer | Quality Assur. | 2024-01-30 | 2024-02-11 | 12 | In Progress | 25% | Low | 4200 | 168 | 50400 | Check formula | In Progress
100 | Combine & Reconcile Columns — Address | Phase 4 | Meera Pillai | PMO | 2024-03-16 | 2024-04-06 | 21 | In Progress | 65% | Critical | 3500 | 60 | 73500 | Needs validation | In Progress
101 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Siddharth Rao | BI & Analytics | 2024-02-17 | 2024-03-09 | 21 | In Progress | 25% | High | 5000 | 100 | 105000 | Check formula | In Progress
102 | Trim Extra Spaces — Customer Name Import | Phase 2 | Rohit Gupta | Business Intel. | 2024-01-01 | 2024-01-29 | 28 | In Progress | 40% | Medium | 5500 | 168 | 154000 | Needs validation | In Progress
103 | Standardize Text Case — Region Codes | Phase 3 | Lakshmi Nair | Data Platform | 2024-01-07 | 2024-01-17 | 10 | In Progress | 50% | Critical | 3500 | 120 | 35000 | Check formula | In Progress
104 | Fix Date Formats — Legacy System Dates | Phase 4 | Rohit Gupta | Quality Assur. | 2024-01-05 | 2024-01-26 | 21 | In Progress | 25% | High | 4200 | 60 | 88200 | Check formula | In Progress
105 | Handle Missing Values — Customer Database | Phase 1 | Priya Sharma | PMO | 2024-02-19 | 2024-03-11 | 21 | In Progress | 75% | Medium | 5000 | 80 | 105000 | — | In Progress
106 | Split Combined Columns — Contact Database | Phase 2 | Amit Roy | BI & Analytics | 2024-01-19 | 2024-01-26 | 7 | Not Started | 0% | Low | 3500 | 120 | 24500 | Verified OK | Not Started
107 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Amit Roy | Business Intel. | 2024-04-19 | 2024-05-17 | 28 | Not Started | 0% | Low | 5000 | 60 | 140000 | — | Not Started
108 | Validate Data Ranges — HR Age Dataset | Phase 4 | Sunita Verma | Data Platform | 2024-01-07 | 2024-01-21 | 14 | In Progress | 100% | Critical | 2000 | 100 | 28000 | — | In Progress
109 | Standardize Category Labels — Product SKU | Phase 1 | Sunita Verma | Quality Assur. | 2024-05-02 | 2024-05-09 | 7 | In Progress | 40% | Critical | 3000 | 140 | 21000 | — | In Progress
110 | Combine & Reconcile Columns — Address | Phase 2 | Arjun Pillai | PMO | 2024-01-09 | 2024-01-16 | 7 | In Progress | 100% | High | 2000 | 160 | 14000 | Verified OK | In Progress
111 | Remove Duplicates — CRM Export Cleaning | Phase 3 | Deepa Krishnan | BI & Analytics | 2024-05-09 | 2024-05-30 | 21 | Not Started | 0% | Critical | 3000 | 60 | 63000 | — | Not Started
112 | Trim Extra Spaces — Customer Name Import | Phase 4 | Neha Joshi | Business Intel. | 2024-03-10 | 2024-03-24 | 14 | In Progress | 100% | Critical | 5500 | 80 | 77000 | Pending review | In Progress
113 | Standardize Text Case — Region Codes | Phase 1 | Neha Joshi | Data Platform | 2024-05-08 | 2024-06-05 | 28 | In Progress | 75% | Low | 5000 | 140 | 140000 | Verified OK | In Progress
114 | Fix Date Formats — Legacy System Dates | Phase 2 | Siddharth Rao | Quality Assur. | 2024-04-26 | 2024-05-10 | 14 | In Progress | 65% | Medium | 4000 | 60 | 56000 | — | In Progress
115 | Handle Missing Values — Customer Database | Phase 3 | Pooja Iyer | PMO | 2024-05-29 | 2024-06-08 | 10 | In Progress | 40% | Medium | 4200 | 80 | 42000 | Verified OK | In Progress
116 | Split Combined Columns — Contact Database | Phase 4 | Ananya Singh | BI & Analytics | 2024-03-11 | 2024-03-23 | 12 | In Progress | 100% | High | 4000 | 80 | 48000 | Check formula | In Progress
117 | Remove Non-Numeric Chars — Revenue Data | Phase 1 | Rohit Gupta | Business Intel. | 2024-04-21 | 2024-05-03 | 12 | In Progress | 50% | Critical | 4200 | 140 | 50400 | — | In Progress
118 | Validate Data Ranges — HR Age Dataset | Phase 2 | Lakshmi Nair | Data Platform | 2024-04-12 | 2024-04-26 | 14 | In Progress | 40% | Critical | 5000 | 80 | 70000 | Needs validation | In Progress
119 | Standardize Category Labels — Product SKU | Phase 3 | Lakshmi Nair | Quality Assur. | 2024-03-13 | 2024-03-25 | 12 | Not Started | 0% | Critical | 4200 | 80 | 50400 | Verified OK | Not Started
120 | Combine & Reconcile Columns — Address | Phase 4 | Lakshmi Nair | PMO | 2024-04-04 | 2024-04-16 | 12 | In Progress | 50% | High | 4200 | 80 | 50400 | Needs validation | In Progress

## Gantt Chart
📅 GANTT CHART — Data Cleaning for Excel Dashboard Development ¦ January 2024 – June 2024 ¦ 4 Phases ¦ 10 Techniques
<-Back
# | Task / Technique | Phase | Owner | Start | End | Days | Status | % Done | Priority | January 2024 |  |  |  | February 2024 |  |  |  | March 2024 |  |  |  | April 2024 |  |  |  | May 2024 |  |  |  | June 2024
[10 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PHASE 1 — Foundation Cleaning (Techniques 1–3)
1 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Priya Sharma | 2024-01-01 | 2024-01-15 | 14 | Completed | 100% | Critical
2 | Trim Extra Spaces — Customer Name Import | Phase 1 | Rahul Mehta | 2024-01-08 | 2024-01-18 | 10 | Completed | 100% | Critical
3
PHASE 2 — Structure & Format Cleaning (Techniques 4–6)
4 | Fix Date Formats — Legacy System Dates | Phase 2 | Amit Roy | 2024-01-29 | 2024-02-12 | 14 | Completed | 100% | Critical
5 | Handle Missing Values — Customer Database | Phase 2 | Sunita Verma | 2024-02-05 | 2024-02-19 | 14 | Completed | 100% | High
6
PHASE 3 — Value Validation & Standardisation (Techniques 7–9)
7 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Amit Roy | 2024-03-04 | 2024-03-18 | 14 | In Progress | 40% | Critical
8 | Validate Data Ranges — HR Age Dataset | Phase 3 | Pooja Iyer | 2024-03-11 | 2024-03-25 | 14 | Not Started | 0% | High
9
PHASE 4 — Data Consolidation & Final QA (Technique 10)
10 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | 2024-04-15 | 2024-04-29 | 14 | Not Started | 0% | Medium
LEGEND | Phase 1 – Foundation | Phase 2 – Structure | Phase 3 – Validation | Phase 4 – Final QA | ■ Completed | ■ In Progress | ■ Not Started

## Resource Planner
👥 RESOURCE ALLOCATION PLANNER — Data Cleaning Project ¦ Team capacity, task assignments, workload & availability — Jan to Jun 2024
← Back to Project Overview
# | Resource Name | Role | Department | Techniques Assigned | Ph.1 | Ph.2 | Ph.3 | Ph.4 | Total Tasks | Daily Rate (₹) | Hours Alloc. | Availability % | Utilisation % | Status
1 | Priya Sharma | Senior Data Analyst | BI & Analytics | COUNTIF, TRIM, CLEAN, VLOOKUP, ISBLANK | 2 | 2 | 1 | 0 | 5 | 3500 | 168 | 90% | 0.5357% | Active
2 | Rahul Mehta | BI Developer | Business Intel. | UPPER/LOWER/PROPER, TEXTSPLIT, LEFT/MID | 1 | 1 | 1 | 0 | 3 | 4000 | 140 | 80% | 0.4762% | Active
3 | Amit Roy | Data Engineer | Data Platform | DATEVALUE, VALUE, DATE, TEXTJOIN | 0 | 1 | 1 | 1 | 3 | 4200 | 160 | 95% | 0.5655% | Active
4 | Sunita Verma | QA Analyst | Quality Assur. | IFERROR, ISBLANK, AVERAGEIFS, IF, AND | 0 | 1 | 1 | 1 | 3 | 3000 | 120 | 70% | 0.4167% | Active
5 | Karan Malhotra | Project Manager | PMO | Project Planning, Reporting, Stakeholder | 1 | 1 | 1 | 1 | 4 | 5000 | 80 | 60% | 0.3571% | Active
6 | Deepa Krishnan | Junior Data Analyst | BI & Analytics | TRIM, CLEAN, VLOOKUP, COUNTIF | 1 | 1 | 0 | 0 | 2 | 2000 | 80 | 100% | 0.5952% | Active
7 | Neha Joshi | Data Architect | Data Platform | Data Modelling, ETL, Schema, Validation | 0 | 0 | 1 | 1 | 2 | 5500 | 60 | 50% | 0.2976% | Part-time
TOTALS / AVERAGES |  |  |  |  | 5 | 7 | 6 | 4 | 22 | 3885.7143 | 808 | 77.86% | 0.4634%
WORKLOAD SUMMARY BY PHASE
Resource | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total Tasks | Hours | Util %
Priya Sharma | 2 | 2 | 1 | 0 | 5 | 168 | 85%
Rahul Mehta | 1 | 1 | 1 | 0 | 3 | 140 | 78%
Amit Roy | 0 | 1 | 1 | 1 | 3 | 160 | 90%
Sunita Verma | 0 | 1 | 1 | 1 | 3 | 120 | 65%
Karan Malhotra | 1 | 1 | 1 | 1 | 4 | 80 | 55%
Deepa Krishnan | 1 | 1 | 0 | 0 | 2 | 80 | 70%
Neha Joshi | 0 | 0 | 1 | 1 | 2 | 60 | 45%

## Task Tracker
✅ TASK TRACKER — Data Cleaning for Excel Dashboard ¦ Detailed task log with formulas, dependencies, review dates & completion tracking
← Back to Project Overview
# | Technique / Task | Phase | Owner | Priority | Start Date | End Date | Duration | Status | % Complete | Notes / Formula Used | Dependency | Review Date | ▶ Live Formula (click me!) | Sample Data (reference)
1 | Remove Duplicates — CRM Export Cleaning | Phase 1 | Priya Sharma | Critical | 2024-01-01 | 2024-01-15 | 14 | In Progress | 100% | COUNTIF($A$2:$A2,A2)>1 ¦ Data > Remove Duplicates | None | 2024-01-17 | FALSE | ORD-1001
2 | Trim Extra Spaces — Customer Name Import | Phase 1 | Rahul Mehta | Critical | 2024-01-08 | 2024-01-18 | 10 | In Progress | 100% | TRIM(CLEAN(A2)) | Task 1 | 2024-01-20 | Priya Sharma | Priya Sharma
3 | Standardize Text Case — Region Codes | Phase 1 | Neha Joshi | High | 2024-01-15 | 2024-01-25 | 10 | In Progress | 100% | PROPER(A2) ¦ UPPER(A2) ¦ LOWER(A2) | Task 2 | 2024-01-27 | North West | north west
4 | Fix Date Formats — Legacy System Dates | Phase 2 | Amit Roy | Critical | 2024-01-29 | 2024-02-12 | 14 | In Progress | 100% | DATEVALUE(A2) ¦ DATE(RIGHT,MID,LEFT) | Task 3 | 2024-02-14 | 45320 | 2024-01-29
5 | Handle Missing Values — Customer Database | Phase 2 | Sunita Verma | High | 2024-02-05 | 2024-02-19 | 14 | In Progress | 100% | IF(ISBLANK(A2),"Unknown",A2) | Task 4 | 2024-02-21 | Unknown
6 | Split Combined Columns — Contact Database | Phase 2 | Karan Malhotra | Medium | 2024-02-12 | 2024-02-24 | 12 | In Progress | 65% | LEFT(A2,FIND(" ",A2)-1) ¦ MID(A2,FIND(...)) | Task 5 | 2024-02-26 | Karan | Karan Malhotra
7 | Remove Non-Numeric Chars — Revenue Data | Phase 3 | Amit Roy | Critical | 2024-03-04 | 2024-03-18 | 14 | In Progress | 40% | VALUE(SUBSTITUTE(SUBSTITUTE(A2,"Rs. ",""),",","")) | Task 6 | 2024-03-20 | 150000 | Rs. 1,50,000
8 | Validate Data Ranges — HR Age Dataset | Phase 3 | Pooja Iyer | High | 2024-03-11 | 2024-03-25 | 14 | Not Started | 0% | IF(AND(A2>=18,A2<=65),"Valid","Invalid") | Task 7 | 2024-03-27 | Valid | 45
9 | Standardize Category Labels — Product SKU | Phase 3 | Siddharth Rao | High | 2024-03-18 | 2024-04-01 | 14 | Not Started | 0% | IFERROR(VLOOKUP(UPPER(A2),MapTable,2,0),PROPER(A2)) | Task 8 | 2024-04-03 | Electronics | electronics
10 | Combine & Reconcile Columns — Address | Phase 4 | Vikram Nair | Medium | 2024-04-15 | 2024-04-29 | 14 | Not Started | 0% | TEXTJOIN(", ",TRUE,B2,C2,D2) | Task 9 | 2024-05-01 | 123 Main St, Mumbai, 400001 | 123 Main St
ADDED VALUE DETAILS |  |  |  |  | STATUS SUMMARY
Name | Column | Detail | Value |  | Status | Count
Duplicate Count | B | Duplicate names in tasks | 1 |  | Completed | 0
Avg Revenue (K) | N | Average cleaned revenue / 1000 | 55.97 |  | In Progress | 97
Total Revenue (Lakh) | N | Total cleaned revenue / 100000 | 67.16 |  | Not Started | 23
Completion % | I | Completed tasks ratio x 100 | 0
On Track % | P | On-track tasks ratio x 100 | 0

## Dashboard Checklist
📋 DASHBOARD READINESS CHECKLIST — Pre-Deployment Quality Gate ¦ Verify all 10 items before connecting cleaned dataset to the Excel Dashboard
← Back to Project Overview
# | Checklist Item | How to Verify | Responsible | Due Date | Status
1 | No duplicate rows | COUNTIF on key column — all values = 1 | Priya Sharma | 2024-01-22 | Completed
2 | No extra spaces in text fields | LEN(TRIM(A2))=LEN(A2) is TRUE for all rows | Rahul Mehta | 2024-01-22 | Completed
3 | Consistent text casing | Unique values in category cols match expected list | Neha Joshi | 2024-02-05 | Completed
4 | All dates are true date serials | ISNUMBER(A2)=TRUE for all date cells | Amit Roy | 2024-02-05 | Completed
5 | No unexpected blank cells | COUNTBLANK returns 0 for all mandatory columns | Sunita Verma | 2024-02-19 | Completed
6 | All numeric fields are numbers | ISNUMBER returns TRUE; no left-aligned numbers | Karan Malhotra | 2024-03-07 | In Progress
7 | Category labels standardised | Pivot on category col; unique count matches expected | Siddharth Rao | 2024-03-21 | In Progress
8 | No out-of-range values | MIN and MAX match expected bounds for each numeric col | Pooja Iyer | 2024-03-21 | Not Started
9 | Data formatted as Excel Table | Ctrl+T applied — enables dynamic named ranges | Deepa Krishnan | 2024-04-05 | Not Started
10 | Backup of raw data retained | Original sheet or workbook copy preserved before cleaning | Vikram Nair | 2024-01-01 | Completed
STATUS SUMMARY | Count
Completed | 0
In Progress | 97
Not Started | 23